## Cover Page
Clinical Safety Hazard Log - Child Protection Information Sharing (CP-IS) Abridged version
Programme | CP-IS | Document Record ID Key
Sub-Prog / Project
Prog. Director |  | Status | Final
Owner | Chris Dickson | Version | 1
Author | Cath Johnson | Version Date | 2025-10-31
Clinical Safety Hazard Log - <project> |  |  | Child Protection Information Sharing (CP-IS)
Document Purpose
This abridged version of the CP-IS FHIR API hazard log is available for the use of suppliers who integrate with CP-IS using the FHIR API. The original scoring of the hazards has been removed. This enables suppliers to review the hazards and their associated causes and score the hazards from the perspective of their own use case.
Copyright © 2018, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre.All Rights Reserved.

## Version History
Amendment History
Version | Date | Amendment History
0.1 | 03/04.2025 | First draft Hazard Log
0.2 | 2025-04-10 | Hazards and causes added after review of FGM and patient flag hazard logs
0.3 | 2025-04-17 | Additional cause added after hazard workshop. John Maw Lead tester reviewed and added controls and test information.
0.4 | 2025-04-22 | Amendments made to explanation of API and MESH in the document by David Fletcher
0.5 | 2025-04-24 | Initial risk assessment scores added by Cath Johnson Clinical Lead and CSO
0.6 | 2025-09-25 | Addition of a new hazard (CP-IS 003) added after the hazard workshop for part 2 of the development. One new cause added to Hazard number 2 (cause 2.3)
0.7 | 2025-10-23 | Addition of residual risk scores
1 | 2025-10-31 | Amendments made after reviewer comments. Uplifted to V1.0
| 2025-11-05 | Clinical Safety Scores and Owner removed from this version prior to sharing with suppliers
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Rudi Redford Brown |  | Safety Engineer CSG | 2025-10-30 | 0.7
Zak Bickhan |  | Clinical Safety Officer CSG | 2025-10-30 | 0.7
Bruno Tcheck |  | Safety Engineer CSG | 2025-10-30 | 0.7
Richard Gurney |  | CSO Patient Flag | 2025-10-24 | 0.7
Seema Varghese |  | Clinical Lead DOSM |  | 1
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Chris Dickson |  | Senior Clinical Lead |  | 1
Distribution
NHS Digital Clinical Safety Personnel
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just need to remove ‘digital’

## Hazard Log
|  | Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  | Existing Controls | [9 empty] | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
CP-IS 001 | 2025-04-10 |  | The patient may experience a delay in care. | HCP or social worker may not be aware of full circumstances in order to provide safeguarding. This may lead to ongoing/further harm to the Child (multiple potential harm outcomes). | 1.1 - Error storing the CP-IS flag due to Patient Flag API failure | CP-IS doesnt create a CP-IS Flag via the Patient Flag API. CP-IS Flags are uploaded by local authorities using batch files sent via MESH. If there is an error processing a CP-IS record, e.g. we can't match the patient to PDS or the record is corrupted, we would reject the update and send a response back to the Local Authority in which case the flag would not be visible on the child's record. PFAPI Testing during development covering RA and FGM (CP-IS uses same underlying Patient Flags functionality) | JIRA Tickets and associated Test Articles demonstrating test evidence DEV Testing https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-425 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-587 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-588 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-717 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-776 INT Testing https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-936 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1108 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1113 Prod Slack channel contains PID so can only be viewed by authorised staff. Second channel supporting INT can be seen. | [8 empty] | CP-IS Testing during Development including Parallel running and Response Comparison with Live Spine system | JIRA Tickets and associated Test Articles demonstrating test evidence | [7 empty] | Error message testing completed and evidence from the parallel run |  | Open
|  | Failure to upload CP-IS Flag due to system failure. |  |  | 1.2 Failure to upload the CP-IS flag due to MESH failure | MESH is a stable product | Existing NHSE MESH data transfers | [17 empty] | MESH is a stable and secure system, handling up to 60 million messages per month, it has been in use since 2016 and is considered highly reliable |  | Open
[5 empty] | 1.3 - Customer attempts to perform a CP-IS update which should be successful but is rejected due to a failure with the CP-IS upload process | There will be parallel running of the existing Spine upload process and the new Patient Flags CP-IS upload process to ensure all records are processed correctly. (This parallel running will cease at Go Live) | Jira Tickets and associated Test Articles demonstrating test evidence DEV Testing https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-425 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-587 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-588 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-717 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-776 INT Testing https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-936 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1108 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1113 Summary of data differences and mitigations found in Safety case | [17 empty] | Parallel running evidence |  | Open
|  | Failure to display CP-IS Flag |  |  | 1.4 System error in Patient Flag when retrieving the CP-IS flag | PFAPI Testing during development covering RA and FGM (CP-IS uses same underlying Patient Flags functionality) | JIRA Tickets and associated Test Articles demonstrating test evidence https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-845 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1037 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1044 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1036 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-852 | [17 empty] | Test evidence and previous testing for FGM and RA - uses the same underlying functionality |  | Open
[5 empty] | 1.5 Lack of response from the Patient Flag API to an end user request | PFAPI Testing during development covering RA and FGM (CP-IS uses same underlying Patient Flags functionality) | JIRA Tickets and associated Test Articles demonstrating test evidence. https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-75 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-77 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-101 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-81 | [17 empty] | Test evidence and previous testing for FGM and RA - uses the same underlying functionality |  | Open
[5 empty] | 1.6 Inadequate end to end testing | The CP-IS team developed deployment verification criteria based on the learning from the 2 previous flag developments (RA and FGM). Further criteria was added specific to CP-IS to ensure as complete test coverage as possible. The Deployment Verification Process (DVP) period will be for 45 consecutive days. During this period a combination of live and test patient data will be tested. A 2 week period will follow this with no changes made to the suppliers estate. This period of time can be tailored if no issues are seen within DVP, as this is a read only service. At the end of a stable period of running on the final build, the DVP sign off is required to move into Full Service Commencement. Providing no changes have been made to the build and the service is stable throughout DVP, stakeholders can agree to exit DVP without a period of stability running. | Deployment verification criteria and plan developed - In Safety Case | [17 empty] | DVC plan (document in safety case) |  | Open
CP-IS 002 | 2025-04-10 | CP-IS flag is held on the system when it shouldn’t be | The patient receives incorrect or inappropriate care | HCP or social worker may think a patient needs further assessment when not necessary causing psychological distress to the patient | 2.1 Customer attempts to make a CP-IS flag removal request which should be successful but is rejected due to a problem with the CP-IS upload process. | There will be parallel running of the existing Spine upload process and the new Patient Flags CP-IS upload process to ensure all records are processed correctly prior to Go Live. The CP-IS test team has undertaken the parallel processing of all the care plan types used for CP-IS including Looked After Child (LAC), Child Protection Plan (CPP) and Unborn Child Plan (UCP) that have been received from the Local Authorities and uploaded into Spine. The automated comparison of the PFAPI responses with the actual responses being returned to the Local Authorities by Spine was checked to ensure that they are identical. The comparison results are logged in real time and any discrepancies are resolved to remove future failures. This process has been running for over 3 months and has processed several thousand files. | Jira Tickets and associated Test Articles demonstrating test evidence DEV Testing https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-425 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-587 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-588 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-717 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-776 INT Testing https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-936 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1108 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1113 | [17 empty] | Parallel running evidence |  | Open
|  | Data is missing, corrupted or incomplete. |  | HCP or social worker may not realise they have incorrect, or missing information for the patient affecting the ability to assess the individual adequately. This may lead to ongoing/further harm to the child. | 2.2 CP-IS data is not migrated correctly from Spine to the Patient Flag data base. | Patient Flags data migration has already been successfully completed for RA and FGM. Parallel processing has been undertaken of all Production Care Plan files received from the Local Authorities and uploaded into Spine and the automated comparison of the PFAPI responses with the actual responses being returned to the Local Authorities by Spine completed, to ensure that they are identical. The comparison results are logged in real time and any discrepancies are resolved to remove future failures. This process has been running for over 3 months and has processed several thousand files. | Jira Tickets and associated Test Articles demonstrating test evidence https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-845 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-854 https://nhsd-jira.digital.nhs.uk/browse/FLAGSAPI-1154 https://nhsd-confluence.digital.nhs.uk/spaces/CLP/pages/1113361633/CP-IS+Production+Cut+Over+Test+Plan+-+INT+environment Note: FLAGSAPI-854 updates the existing Data Migration Script used in RA and FGM Summary of comparisons can be seen here: https://nhs.sharepoint.com/sites/msteams_ab451f/Shared%20Documents/General/Theta/CPIS%20Comparison%20Tool%20Results.xlsx |  |  | Only a minimum amount of CP-IS data is shared which minimises the risk of data corruption. | [5 empty] | Data Validation: Comparisons will be made between the existing spine data and the new Patient Flag service data to ensure they are identical. This involves validating the records and performing reconciliation checks to confirm data integrity. Mitigation Strategies: Mitigation strategies will be put in place to address any potential risks during the migration process, including ensuring that no data is lost and that all records are accurately transferred to the new system. | [8 empty] | Comparison exercise of data migration and management/mitigation of those dfferences |  | Open
| 2025-08-19 | Previous consultation information will be missing from the read only message for the FHIR API users |  | A HCP may believe that if there arent details shared of any previous consultations that this means that there havent been any. This could be misleading, affecting the HCPs ability to assess the sitation fully. | 2.5 During part 1 of the roll out of the FHIR API, there will be a disparity of information shared for existing users and new users of CP-IS. New users using the FHIR API will not receive the 25 last consultation details (Care setting, date and time) for the patient. This issue will be resolved when part 2 of the development is completed and ASN information flows via the new API. This could cause confusion short term for users who work across organisations some of whom are using the existing HL7 API and also will use the new FHIR API, as they will see different levels of ASN information. | [14 empty] | New users will be informed about this during onboarding to CP-IS and information will be added to the website for existing users who may be accessing CP-IS across different care settings using either HL7 or FHIR APIs. Suppliers use a variety of methods: All suppliers have a process for release notes – e.g. ‘this patch will be coming out on this date and the changes will be…..’, practice and ICB/ICS support staff register to receive those release notes. This issue will be added tothe release notes End users advised that NCRS is a system that can be accessed to check CP-IS flags |  |  |  |  | Business change processes introduced to reduce risk of issue causing problems |  | Open
Note on R5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are the references available or is this part of phase 1?

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## References
Reference | Description | Version | Doc. No.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16