## Cover Page
Clinical Safety Hazard Log - FHIR PDS API - API Platform
Programme | Digital Interopability Platform | Document Record ID Key
Sub-Prog / Project | API Platform | API Platform: FHIR PDS-HL-02 (superceding NPFIT-FNT-TO-TOCLNSA-2194)
Prog. Director |  | Status | Approved
Owner | Raman Behl | Version | 4
Author | Sean White | Version Date | 2020-12-18
Clinical Safety Hazard Log - FHIR PDS API - API Platform
Copyright © 2018, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre.All Rights Reserved.

## Version History
Amendment History
Version | Date | Amendment History
0.1 |  | First draft Hazard Log
1 | 2020-03-18 | Release for approval PDS Read Only
2 | 2020-07-24 | Release of PDS Update
2.1 | 2020-11-09 | Assurance of system restricted authentication model for PDS Read only
3 | 2020-12-18 | Formal issue following review and provision of evidence.
5 | 2022-04-28 | Rlease of PDS FHIR API citizen update
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Chris Dickson |  | CSO | 2020-03-16 | 1
Raman Behl |  | CSO | 2020-03-18 | 1
Munish Jokhani |  | Project manager | 2020-03-18 | 1
Chris Dickson |  | CSO | 2020-03-24 | 2
Raman Behl |  | CSO | N/A | 2
Munish Jokhani |  | Project manager | 2020-03-24 | 2
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Chris Dickson |  | CSO | 2020-03-16 | 1
Raman Behl |  | CSO | 2020-03-18 | 1
Munish Jokhani |  | Project manager | 2020-03-18 | 1
Chris Dickson |  | CSO | 2020-03-24 | 2
Raman Behl |  | CSO | N/A | 2
Munish Jokhani |  | Project manager | 2020-03-24 | 2
Raman Behl |  | CSO | 2020-12-18 | 3
Raman Behl |  | CSO | 2021-01-14 | 4
Raman Behl |  | CSO | 2022-04-28 | 5
Distribution
NHS Digital Clinical Safety Personnel
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## FHIR PDS Read Only Hazard Log
|  | Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PDSRO1 | 2020-02-13 | False positive PDS search result returned (single result). On going care compromised due to wrong PDS information returned, impacting ability to 1. Use correct NHS Number 2. Send correspondance to target patient 'A' (Patient B sent Patient A's comms, Patient A sent nothing). 3. Access wrong information / services e.g. SCR, ERS 4. Access the wrong patient medical record a. Clinical decision based on wrong information b. Creation of confused record - Patient A's clinical information could be recorded within patient B' Electronic Clinical Record | Wrong Patient PDS record returned | Potential for Patient A's information to be used / recorded against Patient B's record compromising both patients clinical record and care i.e. Confused record Potential delay to Patient care
PDSRO2 | 2020-02-13 | False negative PDS search result returned (single result). On going care compromised due to lack of PDS information, adversely impacting ability to 1. Confirm NHS Number 2. Send correspondance to patient 3. Access other services e.g. SCR, ERS | No Patient PDS record returned where one exists | Potential delay to Patient care Could lead to creation of duplicate record
PDSRO3 | 2020-02-13 | Multiple PDS search results returned for user to view and select the correct record. On going care compromised due to wrong selection of PDS information, impacting ability to 1. Use INcorrect NHS Number 2. Send correspondance to target patient 'A' (Patient B sent Patient A's comms, Patient A sent nothing). 3. Access wrong information / services e.g. SCR, ERS 4. Access the wrong patient medical record a. Clinical decision based on wrong information b. Creation of confused record - Patient A's clinical information could be recorded within patient B' Electronic Clinical Record | Wrong selection of Patient PDS record | Potential for Patient A's information to be used / recorded against Patient B's record compromising both patients clinical record and care i.e. Confused record Potential delay to Patient care
PDSRO4 | 2020-03-06 | Valid user (authorised ) and/or system fails to authenticate and / or authentication is delayed and/or authorise and therefore cannot retrieve patient details which impacts subsequent care. | No Patient PDS record returned as Service can’t be accessed | Potential delay to Patient care

## FHIR PDS update Only
|  | Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[7 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | SA Risk log reference *for admin purpose only* | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PDSU1 | 2020-06-18 | User is informed of failure with correct error code | Clincian unable to update PDS record of a patient. | Patient identification compromised resulting in delays in accessing patient care records e.g. demographics is
|  | User is not informed of failure |  | Possibility of patient being missed from an extract/report requested by a customer which could lead to patient screening being missed or delayed.
|  | An attempt to make a pds update is rejected however the reason for rejection is not accuratley relayed to the client, |  | Communications to patient sent to wrong destination e.g. address, email, telephone
Demographic information related to the patient record becomes out of date, incomplete or corrupt.
PDS Record can not be accurately updated
PDSU2 | 2020-06-18 | Patients PDS data contains incorrect data | (Client) Clinician or Patient attempts to make a pds update which should be rejected but is successful | Patient identification compromised resulting in delays in accessing patient care records e.g. demographics, pharmacist, mobile number etc which should fail validation ( as required in those circumstances, in line with rules) can result in clinical harm resulting due to PDS information being inaccurate/out of date.
Possibility of patient being missed from an extract/report requested by a customer which could lead to patient screening being missed or delayed.
Communications to patient sent to wrong destination e.g. address, email, telephone
PDSU3 | 2020-06-18 | Patient has more than one electronic record neither one containing a complete or current medical history | Duplicate Patient Record exists potentailly adversly affecting care decisions | Potential for inappropriate treatment as demographic and clinical information may reside over two or more records. Possibility of patient being erroneously excluded/added from/to an extract/report requested by a customer which could lead to patient screening being missed / delayed or wrongly assigned.

## FHIR PDS Citizen Update
|  | Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[7 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | SA Risk log reference *for admin purpose only* | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PDSCU1 | 2022-04-22 | Users of the API Platform are experiencing problems when attempting to use one of the APIs hosted on there | Citizen unable to access PDS record | Potential patient inconvenience as patient unable to view, set/update correct details.
Unable to use PDS FHIR API
Incorrect error message is displayed when unauthorised action takes place (Any Validation) for patient
Patient unable to read their own details
Current users is unable to access the PDS FHIR API
PDSCU2 | 2022-04-22 | Users of the API Platform are experiencing problems when attempting to use one of the APIs hosted on there | Citizen Unable to update their patient record | Potential delay to patient care as patient unable to set/update correct details.
|  | Unable to use PDS FHIR API |  | Potential patient inconvenience as patient unable to view, set/update correct details.
|  | Incorrect error message is displayed when unauthorised action takes place (Any Validation) for patient |  | Communications to patient sent to wrong destination e.g. address, email, telephone, Nominated pharmacy
Patient unable to read their own details
Current users is unable to access the PDS FHIR API
Patient is not able to update details which they are permitted to do so
Patient updates are failing
PDSCU3 | 2022-04-22 | Unauthorised access to the PDS | Wrong citizen /patient record updated | Potential for Patient A's information to be used / recorded against Patient B's record compromising both patients clinical record and care i.e. Confused record Communications to patient sent to wrong destination e.g. address, email, telephone, Nominated pharmacy Potential delay to Patient care
Patient is able to update details for which they don’t have permission to do so

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## References
Reference | Description | Version | Doc. No.
1 | DDC API management team / SA Risk log |  | https://hscic365.sharepoint.com/:x:/s/APIManagement/Ec0NMqxPD9tHpvMg0CKG52YB8rRwxwM2dMzP92oVye2rww?e=86gjQR
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16