## Cover Page
Programme | Strategy, Policy & Governance Directorate | Document Record ID Key
Sub-Prog / Project | Clinical Safety | DFOCVC_Generic_HL
Prog. Director | Manpreet Pujara | Status | FINAL
Owner | GPITF Programme | Version | 2
Author | Pearl Tawana | Version Date | 2022-02-25
DFOCVC Generic Hazard Log
Document Purpose
In order to identify pertinent hazards the following three key areas must be considered: • end to end clinical process, including functionality and how that functionality is used • inter and intra Health IT System messaging • Health IT System architecture and design. This hazard log records generic hazards for Digital First Online Consult Video Consult [DFOCVC] programme, each capability is covered in a separate tab. They are derived from similar Health IT Systems under both normal and fault conditions, provided as a reference only and are not to be considered definitive. They are presented in a consistent form providing a hazard name, description, potential clinical impact, possible cause(s). They must be modified and include additional hazards and or causes specific to the Health IT system under assessment. Hazard assessments, and controls are not provided and should be completed collaboratively by the Manufacturer and Health Organisation from the results of a hazard workshop such as that described in section 4 Clinical Risk analysis of DCB 0129 and DCB 0160 standards. To aid analysis potential causes have been dan be divided into the place holder categories below. Technical e.g. Hardware, software, functional, Non functional, interoperability Human Factor e.g. System and User interaction errors, data entry, navigation Data e.g. Data quality issues - wrong, outdated, corrupt, absent, Process e.g. Process not followed, Health IT system and business process misaligned WHERE APPROPRIATE THIS HAZARD LOG DATA MUST BE INCORPARATED IN TO SUPPLIER'S PRODUCT HAZARD LOG, ELABORATED UPON AND COMPLETED FOR THE SPECIFIC CAPABILITIES, CLINICAL CONTEXT AND IMPLEMANTATION. Contact clinical.safety@nhs.net with any queries or feedback.
Digital First Online Consult & Video Consult Capabilities
Online Consult
Video Consult
Copyright © 2021 NHS Digital
Copyright © 2020, Health and Social Care Information Centre. All Rights Reserved.

## Version History
Amendment History
Version | Date | Amendment History
Draft 9 | 22.06.2021 | NHSE review
1 | 2021-07-07 | Triage tab added
Draft v.1.1 | 2021-10-28 | NHSD review and restructure
Draft v.1.2 | 2022-01-13 | NHSD review and restructure
Draft v.1.3 | 2022-01-17 | NHSD review and restructure
Draft v.1.4 | 2022-01-21 | NHSD review and restructure
Draft v.1.5 | 2022-01-27 | NHSD review and restructure
2 | 2022-02-25 | CSO Approval and uplift to version 2.0
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
NHSE |  | Digital First Primary Care | 22.06.2021 | Draft 9
Sean White |  | Principal Safety Engineer | 2022-01-27 | Draft v.1.5
Hannah McCann |  | Safety Engineer | 2022-01-27 | Draft v.1.5
Neill Jones |  | CSO | 2022-02-04 | Draft v.1.5
NHSE |  | Digital First Primary Care | 2022-02-10 | Draft v.1.5
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Dr Neil Jones |  | Clinical Safety Officer | 2021-07-07 | 1
Dr Neil Jones |  | Clinical Safety Officer | 2022-02-25 | 2
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.
Copyright © 2021 NHS Digital

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Consequence Category | Interpretation
| High | 2 | 3 | 3 | 4 | 5 |  | Consequence | Patients Affected
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Consequence | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
[8 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| 5 | Unacceptable level of risk | [5 empty] | Severe psychological trauma | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
[8 empty] | Severe psychological trauma | Single
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term. | Multiple
[8 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical | [5 empty] | Significant psychological trauma | Single
[8 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 1 | Acceptable, no further action required | [5 empty] | Minor psychological upset; inconvenience | Multiple
[7 empty] | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
[7 empty] | Likelihood Category | Interpretation
[7 empty] | Very high | Certain or almost certain; highly likely to occur
[7 empty] | High | Not certain but very possible; reasonably expected to occur in the majority of cases
[7 empty] | Medium | Possible
[7 empty] | Low | Could occur but in the great majority of occasions will not
[7 empty] | Very low | Negligible or nearly negligible possibility of occurring
Copyright © 2021 NHS Digital

## OnlineConsult
Online consultation
| Description: The description detail is used as background information to help suppliers understand the requirement in more detail, and therefore will not be evaluated. The Online Consultation Capability allows Patients/Service Users/Proxies to request and receive support relating to healthcare concerns, at a time and place convenient for them. Provision of information by the Patient/Service User/Proxy allows the Health or Care Professional dealing with the request to triage requests effectively and make informed decisions about how best to respond - the response could be information or advice, an offer of a consultation, provision of a repeat prescription or a referral to other services. This may be enhanced by the ability to link the request, and the response, to the Patient/Service User's record. The Capability may provide the Patient/Service User/Proxy with instant self-help advice or sign-post them to relevant services. It also supports the remote delivery of a range of clinical scenarios, including: Clinical consultation Direct care advice (from a Health or Care Professional) Report symptoms Review of a known problem or condition |  |  |  |  | To aid analysis potential causes can be divided into the place holder categories below. Technical e.g. Hardware, software, functional, Non functional, interoperability Human Factor e.g. System and User interaction errors, data entry, navigation Data e.g. Data quality issues - wrong, outdated, corrupt, absent, Business Process e.g. Process not followed, Health IT system and business process misaligned THIS HAZARD LOG MUST BE ELABORATED UPON AND COMPLETED FOR THE SPECIFIC CAPABILITIES, CLINICAL CONTEXT AND IMPLEMANTATION.
|  | Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
OC1.1 |  | Clinical decision based on information relating to the wrong patient. | Patient receives inappropriate care | Examples of harm to consider may include: 1. Emotional distress (e.g. Wrong patient may be treated inappropriately based on information entered on record in error). 2. Deterioration of patient condition (e.g. Patient's presenting condition may not be treated and or deteriorate). 3. Death (e.g. Anaphylactic reaction to prescribed treatment resulting in death). Note to Supplier: Please consider harm outcomes within the clinical context that system is intended for use. Harm outcomes should be expressed in the patient context. | Technical Human factor Data Business process Note to Supplier: Please consider and describe specific causes relevent to system. Look at each of the suggested Effects (column C), consider if they are relevent and if so identify what might cause them. These causes may be Technical; Human factor; Data or Business process related. It is beneficial to consider causes in relation to the clinical context and setting that the system is intended to be used. | Note to supplier: Please explain how each cause is mitigated by the identified controls.
Example of cause: 1.1a. System UI: manual patient selection design
OC1.2 |  | Incorrect information received by HCP and/or patient. |  |  | Technical Human factor Data Business process
Example of cause: 1.2a. Algorithm error/ Algorithm does not include important clinical or demographical questions (i.e relating to pregnancy) that may inform clinical decision making.
OC1.3 |  | Information held on system/patient record is not available when clinical decision is made. |  |  | Technical Human factor Data Business process
Example of cause: 1.3a. Role Based Access (RBAC) mapping error
OC1.4 |  | Online consultation system used where it is clinically inappropriate eg: Patient's presenting condition may not be appropriate for Online consultation access. |  |  | Technical Human factor Data Business process
Example of cause: 1.4a. System fails to display alert warning patients of situations where online consultation is not appropriate to use e.g in an emergency situation.
OC1.5 |  | Loss of clinical information held on system/patient record. |  |  | Technical Human factor Data Business process
Example of cause: 1.5a. Integration failure between OC and HCP system
OC2.1 |  | Patient isn't responded to (or does not receive a response) in a therapeutic timescale for the context, including: -Red flags -Emergencies -Urgent care -Safeguarding | Patient care is delayed | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 2.1a. System algorithm (CDS) errors e.g. identification of red flags
OC2.2 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request |  |  | Technical Human factor Data Business process
Example of cause: 2.2a. System design errors - does not present information to HCP in an accessible or user friendly format
OC3.1 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request | Patient does not receive care | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 3.1a: System does not effectively notify patient or HCP of incoming communication
The hazards below may be applicable Health Organisation Clinical Risk Management under DCB 0160
OC4.1 |  | Diagnostic and treatment decisions without full clinical testing that would normally be expected. Tendency to be over cautious proceeding with treatment where they would otherwise seek confirmation of diagnosis e.g. prescribing antibiotics | Patient receives inappropriate care | 1. Emotional distress (e.g. Wrong patient may be treated inappropriately based on information entered on record in error). 2. Deterioration of patient condition (e.g. Patient's presenting condition may not be treated and or deteriorate). 3. Death (e.g. Anaphylactic reaction to prescribed treatment resulting in death). Note to Health Organisation: Please consider harm outcomes within the clinical context that system is intended for use. It may be beneficial to consider patient population demographics and prevalent health conditions. | Technical Human factor Data Business process Note to Health Organisation: Please consider and describe specific causes of the effect relevent to system and practice. These causes may be Technical; Human factor; Data or Business process related. It may be beneficial to consider causes in relation to the clinical context and setting that the system is intended to be used. Look at each of the suggested Effects (column C), consider if they are relevent and if so identify what might cause them.
Example of cause: 4.1a. Online consultation used where its clinically inappropriate, i.e. beyond the technical ability of the system or beyond the Care providers knowledge.
OC4.2 |  | Clinical decision based on information relating to the wrong patient. |  |  | Technical Human factor Data Business process
Example of cause: 4.2a. HCP user error
OC4.3 |  | Incorrect information received by HCP and/or patient. |  |  | Technical Human factor Data Business process
Example of cause: 4.3a: Patient data entry errors
OC4.4 |  | Information held on system/patient record is not available when clinical decision is made. |  |  | Technical Human factor Data Business process
Example of cause: 4.4a: HCP cannot log in to the system due to forgotten password
OC4.5 |  | Online consultation system used where it is clinically inappropriate eg: Patient's presenting condition may not be appropriate for Online consultation access. |  |  | Technical Human factor Data Business process
Example of cause: 4.5a. Patient lacks the skills or capacity to use the system effectively
OC4.6 |  | Loss of clinical information held on system/patient record. |  |  | Technical Human factor Data Business process
Example of cause: 4.6a. Inappropriate deletion of onlince consultation form
OC5.1 |  | Patient isn't responded to (or does not receive a response) in a therapeutic timescale for the context, including: -Red flags -Emergencies -Urgent care -Safeguarding | Patient care is delayed | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 5.1a. Out of date patient contact details or access needs
OC5.2 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request |  |  | Technical Human factor Data Business process
Example of cause: 5.2a. User error
OC5.3 |  | In-efficient use of resource, increase in rescheduled and or follow up consultations due to limitations of Online consultation (Clinician is not able to achieve full confidence in the quality of consultation). Leading to additional consultations for the same episode of care. |  |  | Technical Human factor Data Business process
Example of cause: 5.3a. Patient selects inappropriate consultation format
OC5.4 |  | In-efficient use of resource, increase in patient repeat requests or telephone calls due to limitations in communications |  |  | Technical Human factor Data Business process
Example of cause: 5.4a. Published practice information does not adequately inform patients what to expect when using the system
OC5.5 |  | Practice is lacking capacity or overwhelmed with demand so is unable to clinically triage all incoming online consultation requests to determine the level of urgency or respond in the expected timeframe |  |  | Technical Human factor Data Business process
Example of cause: 5.5a. Communications not configurable to reflect practice workflows, capacity and expectations over weekends/bank holidays/out of hours
OC6.1 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request | Patient does not receive care | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 6.1a. User error
Copyright © 2022 NHS Digital
HOME↓

## VideoConsult
Video consultation
| Description: The description detail is used as background information to help suppliers understand the requirement in more detail, and therefore will not be evaluated. The Video Consultation Capability allows Patients/Service Users/Proxies to request and receive support relating to healthcare concerns, at a time and place convenient for them. Provision of information by the Patient/Service User/Proxy allows the Health or Care Professional dealing with the request to triage requests effectively and make informed decisions about how best to respond - the response could be information or advice, an offer of a consultation, provision of a repeat prescription or a referral to other services. This may be enhanced by the ability to link the request, and the response, to the Patient/Service User's record. The Capability may provide the Patient/Service User/Proxy with instant self-help advice or sign-post them to relevant services. It also supports the remote delivery of a range of clinical scenarios, including: Clinical consultation Direct care advice (from a Health or Care Professional) Report symptoms Review of a known problem or condition |  |  |  |  | To aid analysis potential causes have been dan be divided into the place holder categories below. Technical e.g. Hardware, software, functional, Non functional, interoperability Human Factor e.g. System and User interaction errors, data entry, navigation Data e.g. Data quality issues - wrong, outdated, corrupt, absent, Business process e.g. process not followed, Health IT system and business process misaligned THIS HAZARD LOG MUST BE ELABORATED UPON AND COMPLETED FOR THE SPECIFIC CAPABILITIES, CLINICAL CONTEXT AND IMPLEMANTATION.
|  | Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business process | [5 empty] | HIT Design |  | User Training |  | Business process Change
|  | Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
VC1.1 |  | Clinical decision based on information relating to the wrong patient. | Patient receives inappropriate care | Examples of harm to consider may include: 1. Emotional distress (e.g. Wrong patient may be treated inappropriately based on information entered on record in error). 2. Deterioration of patient condition (e.g. Patient's presenting condition may not be treated and or deteriorate). 3. Death (e.g. Anaphylactic reaction to prescribed treatment resulting in death). Note to Supplier: Please consider harm outcomes within the clinical context that system is intended for use. Harm outcomes should be expressed in the patient context. | Technical Human factor Data Business process Note to Supplier: Please consider and describe specific causes relevent to system. Look at each of the suggested Effects (column C), consider if they are relevent and if so identify what might cause them. These causes may be Technical; Human factor; Data or Business process related. It is beneficial to consider causes in relation to the clinical context and setting that the system is intended to be used. | Note to supplier: Please explain how each cause is mitigated by the identified controls.
Example of cause: 1.1a. System UI: manual patient selection design
VC1.2 |  | Incorrect information received by HCP and/or patient. |  |  | Technical Human factor Data Business process
Example of cause: 1.2a. Algorithm error/ Algorithm does not include important clinical or demographical questions (i.e relating to pregnancy) that may inform clinical decision making.
VC1.3 |  | Information held on system/patient record is not available when clinical decision is made. |  |  | Technical Human factor Data Business process
Example of cause: 1.3a. Role Based Access (RBAC) mapping error
VC1.4 |  | Video consultation system used where it is clinically inappropriate eg: Patient's presenting condition may not be appropriate for Video consultation |  |  | Technical Human factor Data Business process
Example of cause: 1.4a. System fails to display alert warning patients of situations where online consultation is not appropriate to use e.g in an emergency situation.
VC1.5 |  | Loss of clinical information held on system/patient record. |  |  | Technical Human factor Data Business process
Example of cause: 1.5a. Integration failure between VC and HCP system
VC2.1 |  | Patient isn't responded to (or does not receive a response) in a therapeutic timescale for the context, including: -Red flags -Emergencies -Urgent care -Safeguarding | Patient care is delayed | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
[5 empty] | Example of cause: 2.1a. System algorithm (CDS) errors e.g. identification of red flags | [20 empty] | maybe more applicable to DCB0160
VC2.2 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request |  |  | Technical Human factor Data Business process | [20 empty] | maybe more applicable to DCB0160
Example of cause: 2.2a. System design errors - does not present information to HCP in an accessible or user friendly format
VC3.1 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request | Patient does not receive care | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 3.1a: System does not effectively notify patient or HCP of incoming communication
The hazards below may be applicable Health Organisation Clinical Risk Management under DCB 0160
VC4.1 |  | Diagnostic and treatment decisions without full clinical testing that would normally be expected. Tendency to be over cautious proceeding with treatment where they would otherwise seek confirmation of diagnosis e.g. prescribing antibiotics | Patient receives inappropriate care | 1. Emotional distress (e.g. Wrong patient may be treated inappropriately based on information entered on record in error). 2. Deterioration of patient condition (e.g. Patient's presenting condition may not be treated and or deteriorate). 3. Death (e.g. Anaphylactic reaction to prescribed treatment resulting in death). Note to Health Organisation: Please consider harm outcomes within the clinical context that system is intended for use. It may be beneficial to consider patient population demographics and prevalent health conditions. | Technical Human factor Data Business process Note to Health Organisation: Please consider and describe specific causes of the effect relevent to system and practice. These causes may be Technical; Human factor; Data or Business process related. It may be beneficial to consider causes in relation to the clinical context and setting that the system is intended to be used. Look at each of the suggested Effects (column C), consider if they are relevent and if so identify what might cause them.
Example of cause: 4.1a. Video consultation used where its clinically inappropriate, i.e. beyond the technical ability of the system or beyond the Care providers knowledge.
VC4.2 |  | Clinical decision based on information relating to the wrong patient. |  |  | Technical Human factor Data Business process
Example of cause: 4.2a. HCP user error
VC4.3 |  | Incorrect information received by HCP and/or patient. |  |  | Technical Human factor Data Business process
Example of cause: 4.3a: Patient data entry errors
VC4.4 |  | Information held on system/patient record is not available when clinical decision is made. |  |  | Technical Human factor Data Business process
Example of cause: 4.4a: HCP cannot log in to the system due to forgotten password
VC4.5 |  | Video consultation system used where it is clinically inappropriate eg: Patient's presenting condition may not be appropriate for Video consultation access. |  |  | Technical Human factor Data Business process
Example of cause: 4.5a. Patient lacks the skills or capacity to use the system effectively
VC4.6 |  | Loss of clinical information held on system/patient record. |  |  | Technical Human factor Data Business process
Example of cause: 4.6a. Inappropriate deletion of video consultation data
VC5.1 |  | Patient isn't responded to (or does not receive a response) in a therapeutic timescale for the context, including: -Red flags -Emergencies -Urgent care -Safeguarding | Patient care is delayed | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 5.1a. Out of date patient contact details or access needs
VC5.2 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request |  |  | Technical Human factor Data Business process
Example of cause: 5.2a. User error
VC5.3 |  | In-efficient use of resource, increase in rescheduled and or follow up consultations. Leading to additional consultations for the same episode of care. |  |  | Technical Human factor Data Business process
Example of cause: 5.3a. Patient selects inappropriate consultation format
VC5.4 |  | In-efficient use of resource, increase in patient repeat requests or telephone calls due to limitations in communications |  |  | Technical Human factor Data Business process
Example of cause: 5.4a. Published practice information does not adequately inform patients what to expect when using the system
VC5.5 |  | Practice is lacking capacity or overwhelmed with demand so is unable to clinically triage all incoming video consultation requests to determine the level of urgency or respond in the expected timeframe |  |  | Technical Human factor Data Business process
Example of cause: 5.5a. Communications not configurable to reflect practice workflows, capacity and expectations over weekends/bank holidays/out of hours
VC6.1 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request | Patient does not receive care | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 6.1a. User error
Copyright © 2022 NHS Digital
HOME↓

## Clinical Triage
Online Triage
| Description: The description detail is used as background information to help suppliers understand the requirement in more detail, and therefore will not be evaluated. Clinical triage added to this generic hazard log as DFOCVC submissions often include Clinical triage over and above the frame work capabilities. Note there is two kind of triage, 1.Triage where a algorithmic decision determines patient redirection, this almost certainly warrants assessments against Medical Device Regulations - refer to MHRA for further information. 2. System Triage where system collects clinical information where a Clinician makes triage redirection decisions |  |  |  |  | To aid analysis potential causes have been divided into the place holder categories below. Technical e.g. Hardware, software, functional, Non functional, interoperability Human Factor e.g. System and User interaction errors, data entry, navigation Data e.g. Data quality issues - wrong, outdated, corrupt, absent, Business Process e.g. Process not followed, Health IT system and business process misaligned THIS HAZARD LOG MUST BE ELABORATED UPON AND COMPLETED FOR THE SPECIFIC CAPABILITIES, CLINICAL CONTEXT AND IMPLEMANTATION.
|  | Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
CT1.1 |  | Clinical decision based on information relating to the wrong patient. | Patient receives inappropriate care | Examples of harm to consider may include: 1. Emotional distress (e.g. Wrong patient may be treated inappropriately based on information entered on record in error). 2. Deterioration of patient condition (e.g. Patient's presenting condition may not be treated and or deteriorate). 3. Death (e.g. Anaphylactic reaction to prescribed treatment resulting in death). Note to Supplier: Please consider harm outcomes within the clinical context that system is intended for use. Harm outcomes should be expressed in the patient context. | Technical Human factor Data Business process Note to Supplier: Please consider and describe specific causes relevent to system. Look at each of the suggested Effects (column C), consider if they are relevent and if so identify what might cause them. These causes may be Technical; Human factor; Data or Business process related. It is beneficial to consider causes in relation to the clinical context and setting that the system is intended to be used. | Note to supplier: Please explain how each cause is mitigated by the identified controls.
Example of cause: 1.1a. Error in patient verification process
CT1.2 |  | Patient and /or HCP receive the wrong information (e.g. incorect diagnosis based on information inputted) |  |  | Technical Human factor Data Business process
Example of cause: 1.2a. System algorithm errors
CT1.3 |  | Patient and /or HCP receive the wrong information (e.g request for consultation is incorrectly prioritised) |  |  | Technical Human factor Data Business process
Example of cause: 1.3a. System does not enable manual triage/human review if disagreement with outcome
CT1.4 |  | Patient and /or HCP receive the wrong information (e.g patient is signposted to an inappropriate service) |  |  | Technical Human factor Data Business process
Example of cause: 1.4a. Directory of services not up to date
CT1.5 |  | Patient and /or HCP receive the wrong information (e.g interface displays most serious but rare diagnosis vs most common/likely diagnosis to patient) |  |  | Technical Human factor Data Business process
Example of cause: 1.5a. System design
CT1.6 |  | Patient and /or HCP receive the wrong information (e.g presentation of information can be misinterpretted) |  | Examples of harm to consider may include: 1. Emotional distress (e.g. Wrong patient may be treated inappropriately based on information entered on record in error). 2. Deterioration of patient condition (e.g. Patient's presenting condition may not be treated and or deteriorate). 3. Death (e.g. Anaphylactic reaction to prescribed treatment resulting in death). Note to Supplier: Please consider harm outcomes within the clinical context that system is intended for use. Harm outcomes should be expressed in the patient context. | Technical Human factor Data Business process
Example of cause: 1.6a. System UI design
CT1.7 |  | Red flag missed |  |  | Technical Human factor Data Business process
Example of cause: 1.7a. The system design has not adequately considered all possible uses and their consequences
CT1.8 |  | Patient routed through wrong pathway |  |  | Technical Human factor Data Business process
Example of cause: 1.8a. Algorithm error
CT1.9 |  | Pathway not complete |  |  | Technical Human factor Data Business process
Example of cause: 1.9a. System does not save incomplete or failed triage request information or send to practice
CT1.10 |  | Incorrect generation or loss of online consultation record |  |  | Technical Human factor Data Business process
Example of cause: 1.10a. Integration failure
CT2.1 |  | Error, Delay or failure in Clinical Communication | Patient care is delayed | 1. Delayed diagnosis and treatment of condition resulting in deterioration of patient 2. Delay in urgent referral for emergency treatment resulting in severe harm 3. Emotional distress | Technical Human factor Data Business process
Example of cause: 2.1a. System does not save incomplete or failed triage request information or send to practice
CT2.2 |  | Error, Delay or failure in Clinical care due to lack of timely clinical triage by HCP |  |  | Technical Human factor Data Business process
Example of cause: 2.2a. Poor visibility of high priority work items for clinician
The hazards below may be applicable Health Organisation Clinical Risk Management under DCB 0160
CT3.1 |  | Clinical decision based on information relating to the wrong patient. | Patient receives inappropriate care | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 4.2a. HCP user error
CT3.2 |  | Incorrect information received by HCP and/or patient. |  |  | Technical Human factor Data Business process
Example of cause: 4.3a: Patient data entry errors
CT3.3 |  | Information held on system/patient record is not available when clinical decision is made. |  |  | Technical Human factor Data Business process
Example of cause: 4.4a: HCP cannot log in to the system due to forgotten password
CT3.4 |  | Online consultation system used where it is clinically inappropriate eg: Patient's presenting condition may not be appropriate for Online consultation access. |  |  | Technical Human factor Data Business process
Example of cause: 4.5a. Patient lacks the skills or capacity to use the system effectively
CT3.5 |  | Loss of clinical information held on system/patient record. |  |  | Technical Human factor Data Business process
Example of cause: 4.6a. Inappropriate deletion of Clinical triage form
CT4.1 |  | Patient isn't responded to (or does not receive a response) in a therapeutic timescale for the context, including: -Red flags -Emergencies -Urgent care -Safeguarding | Patient care is delayed | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 5.1a.Patient is not aware that clinical triage system is not appropriate for use in emergency
CT4.2 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request |  |  | Technical Human factor Data Business process
Example of cause: 5.2a. User error
CT4.3 |  | In-efficient use of resource, increase in rescheduled and or follow up consultations due to limitations of Clinical triage (Clinician is not able to achieve full confidence in the quality of clinical triage). Leading to additional consultations for the same episode of care. |  |  | Technical Human factor Data Business process
Example of cause: 5.3a. Patient data entry error
CT4.4 |  | In-efficient use of resource, increase in patient repeat requests or telephone calls due to limitations in communications |  |  | Technical Human factor Data Business process
Example of cause: 5.4a. Published practice information does not adequately inform patients what to expect when using the system
CT4.5 |  | Practice is lacking capacity or overwhelmed with demand so is unable to review clinical triage requests by system to confirm the level of urgency or respond in the expected timeframe |  |  | Technical Human factor Data Business process
Example of cause: 5.5a. Communications not configurable to reflect practice workflows, capacity and expectations over weekends/bank holidays/out of hours
CT5.1 |  | Clinical decisions and/or patient outcomes cannot be reached within the consultation request | Patient does not receive care | 1. Emotional distress 2. Deterioration of patient condition. 3. Death | Technical Human factor Data Business process
Example of cause: 6.1a. User error
HOME↓