# Appendix B – Implementation Plan

| Task Name | Indicative Duration | Start Date | Finish Date | Predecessors | Resource Names |
| --- | --- | --- | --- | --- | --- |
| Project Management, Stakeholder Engagement & Governance | 100 days |  |  |  |  |
| 1. Confirm senior support | 5 days |  |  |  |  |
| 2. Identify a project lead | 1 day |  |  |  |  |
| 3. Confirm settings - Scheduled or unscheduled | 2 days |  |  | 2 |  |
| 4. Identify project team members | 5 days |  |  | 1,2 |  |
| 5. ensure familiarity with CP-IS implementation guidance and general requirements | 1 day |  |  | 1,2,3,4, |  |
| 6. Agree how decisions will be made | 1 day |  |  | 1,2,4 |  |
| 7. Agree high level implementation plan, target go live date and method to monitor progress | ongoing |  |  | 2,3,4,5 |  |
| 8. Identify and speak to key stakeholders about CP-IS (and plan how you will keep them informed) | 3 days |  |  | 3,5 |  |
| Access & Smartcards | 35 days |  |  |  |  |
| 9a. Obtain NHS Smartcards and Smartcard readers (for NCRS users only) |  |  |  |  |  |
| 9b. Obtain access to CP-IS (for integrated solution users only) | 21 days |  |  | 11, 17 |  |
| 10. Add Role Based Access Control codes to NHS Smartcards and confirm access | 14 days |  |  | 9, 17 |  |
| Technical | 16 days |  |  |  |  |
| 11. Confirm the technical route to implementation | 3 days |  |  | 1,5,6 |  |
| 12a. Assess current use of NCRS (NCRS users only) |  |  |  |  |  |
| 12b. Confirm Spine/PDS connection (non-NCRS users only) | 3 days |  |  | 3,11 |  |
| 13. Liaise with your IT support team to ensure systems and web browsers are compatible (Only applies if the site didn’t already have NCRS or integrated PDS access). | 1 day |  |  | 3,11,12 |  |
| 14. Update your organisation’s business continuity plans (for technical/system recovery) | 5 days |  |  | 11,15,16,17 |  |
| Business Processes | 63 days |  |  |  |  |
| 15. Map your existing safeguarding processes | 3 days |  |  | 3,4 |  |
| 16. Adapt your safeguarding processes to accommodate CP-IS | 5 days |  |  | 11,15 |  |
| 17. Identify CP-IS access requirements (smartcard or multifactor authentication) | 3 days |  |  | 16 |  |
| 18. Test procedures and processes | 2 days |  |  | 10,11,13 |  |
| 19. Design and deliver training | 14 days |  |  | 11,16,18 |  |
| 20. Update your safeguarding business continuity plans | 3 days |  |  | 16 |  |
| 21. Update information governance policies and training materials | 2 days |  |  | 5,10,11,15 |  |
| Go Live / Managing the live service | 41 days |  |  |  |  |
| 22. Confirm target go live date | 1 day |  |  | 10,16,18,11 |  |
| 23. Prepare to transfer CP-IS to live service | 5 days |  |  | 9,10,12,17,19,11 |  |
| 24. Communicate internally and externally before and after go-live | 5 days |  |  | 1,8,18,22,23 |  |
| 25. Consider readiness to go live | 1 day |  |  | 10,16,18,19,23,11 |  |
| 26. Go live | 1 day |  |  | 25 |  |