# Health care settings - CP-IS Go Live Checklist

A Go/No Go call will take place between assigned NHS Digital Implementation Manager and the Project Lead plus a representative from Safeguarding / IT / system supplier (as appropriate).  The purpose of this call is to ensure that all dependencies on the below checklist have been met prior to live implementation of CP-IS, and any exceptions /proposed resolution noted accordingly to advise a go/no go decision.  More detail on each of the component tasks is available in the Step by Step Guide and Implementation Plan for CP-IS Implementation.  Following the call, the completed checklist will be shared with all parties to confirm accuracy or request any points of correction within 5 working days.

Organisation: 			Date:

Participants of pre go live call:			Technical solution used:

| Task | Project Management, stakeholder engagement & governance | Supporting documentation | Completed | Notes/ Additional Information |
| --- | --- | --- | --- | --- |
| 1-7 | Project set up CPIS Lead (BAU) in place | - LOAs signed/ evidence of commitment from senior decision maker | Yes / No Yes / No |  |
|  | Access and Smartcards |  |  |  |
| 9a/9b | NHS Smartcards and readers obtained (SCRa users) / Obtain access to CP-IS (integrated solutions) |  | Yes / No |  |
| 10 | RBACs added to NHS Smartcards and allocated to required staff (B0107 View Child Protection Plan & B0264 Access SCRa - perform patient trace) All relevant staff have CP-IS access / can see CP-IS tab (ensuring 24/7 coverage) Is responsibility established for reviews of CP-IS/smartcard access? | - Verification via test patient records | Yes / No |  |
| Task | Technical |  |  |  |
| 11-13 | CP-IS configuration & testing completed (including Spine/PDS connection) |  | Yes / No |  |
| 14 | Technical Business Continuity Plans (IT system continuity) updated and relevant staff aware of roles and responsibilities | - Business Continuity Plan | Yes / No |  |
|  | Business Processes |  |  |  |
| 15-17 | Safeguarding processes and flows updated and checked | - Privacy Statement - Safeguarding processes (inc data/information exchanges with external partners) - Standard Operating Procedure - Process maps | Yes / No |  |
| 18 | Test procedures and processes: - Updated safeguarding process verified with in scope staff - Staff aware of roles and responsibilities for viewing CPPs and ASN generation | - Log date, any issues from testing and resolution | Yes / No |  |
| 19 | Staff Training/Awareness delivered: - How CP-IS works and why it’s needed - How CP-IS fits within your existing safeguarding procedures - CP-IS business processes including checking flag, viewing data, follow up actions (including maternity staff and processes) - Who to contact if they have a query about CP-IS - Flag only viewed when the child presents - Benefits of the CP-IS service and how the data supports better safeguarding / patient care - Reminder that the ASN is not a referral and direct action may be required - Routine checks to monitor how staff are using the service, obtain feedback and update business processes accordingly Is a process in place for reviewing and updating staff training in CP-IS? | - Training guides - Confirm number of staff trained across which settings | Yes / No |  |
| 20 | Safeguarding Business Continuity Plan (staff training, business processes) updated and staff aware of roles and responsibilities | - Business Continuity Plan | Yes / No |  |
| 21 | Updated IG policies and training materials | - IG Lead consulted - IG policy updated | Yes / No |  |
|  | Go live and managing the live service |  |  |  |
| 22 | Target go live date still applicable? |  | **/**/** |  |
| 23 | Live service arrangements in place: ## Has a local business owner /effective governance been put in place for the CP-IS service? (Has a shared mailbox address been provided to NHS Digital?) - Is a method in place to monitor utilisation and ensure patterns of CP-IS usage are being reviewed and acted upon? - Is there an owner(s) for checking the system is working as it should (especially following any changes to technical configuration for integrated solutions)? - Is a date set or process in place for future review of relevant business processes (e.g. safeguarding, privacy, business continuity)? - Are any mechanisms in place for tracking and sharing benefits of CP-IS service? - Are mechanisms in place to communicate to staff regarding the CP-IS service (e.g. any changes to business processes, benefits realised)? - Are staff clear on the Incident Process and points of contact within NHS D, local service desks etc? | - Named business owner and ongoing service governance - Standard Operating Procedure - Outstanding R&I - Business Processes and review dates | Yes / No Yes / No Yes / No Yes / No Yes / No Yes / No Yes / No |  |
| 24 | Communicate internally and externally regarding imminent go live and implications esp CP-IS Project team, primary LA’s, CCG, service/help desks | - Communications Plan | Yes / No |  |

| Above checklist completed as record of the current status of this CP-IS deployment: |  |
| --- | --- |
| Checklist and pre go live call completed by (name of IM, NHS Digital): |  |
| Known issues/work off plan for: - Next no/go no call or - Post go live resolution |  |
| Target date for 8wk post go live check: |  |