## Version Control
HSCN Migration Checklist
Directorate/Programme: |  | Health and Social Care Network (HSCN)
Document filename: |  | HSCN CNSP to CNSP Migration Checklist
Version: |  | 1
Published Date: |  | 2022-02-07
Version | Date | Summary of Changes
0.1 | 2021-10-19 | Initial draft
0.2 | 2021-11-03 | Removal of 'Recommendation' column (not applicable); addition of CNSP feedback column (H) & narrative/text boxes for additional 'gap' items to be added by CNSP from row 67
0.3 | 2021-11-10 | Revised version post Technical team review (Andy McAnaney)
0.4 | 2021-11-12 | Revised version post Technical (IPAM) review
0.5 | 2021-11-12 | Revised version post removal of all development notes in commented cells
0.6 | 2021-11-12 | Procurement RM3825 milestone wording checked and approved
0.7 | 2021-11-24 | Revised version including Notes from CNSP call
0.8 | 2021-11-25 | Revised version including amendments post CNSP review on 24/11/21
0.9 | 2021-11-29 | Revised version including amendments post NHSD review on 29/11/21
0.1 | 2021-12-02 | Revised version including consistency checks and post CNSP adds
1 | 2022-02-07 | Final version to be placed on website

## Migration Checklist v.1.0
HSCN CNSP to CNSP Migration Checklist
The table below provides a checklist of activities that should be completed by each Consumer organisation to prepare and perform the migration from legacy CNSP to a new CNSP HSCN access connection. For further advice, Customers should consult their new Consumer Network Service Provider (or CNSP).
Activity Legend/Phases: PO = Pre-Ordering, OR = Ordering, PI = Pre-Installation, PRM = Pre-Migration, MI = Migration, POM = Post Migration
Phase | Ref | Item | Description of requirement | Guidance to Customer
Pre-Ordering | Pre-Ordering
| PO01 | Service Reference | Identify the Service Reference (SR) for each 'legacy' circuit/service to be migrated. This will be required by the new CNSP for the ordering, forecasting and migration processes.
| PO02 | Organisation Data Service (ODS) Code | If the customer is new to HSCN and/or does not have an Organisation Data Service (ODS) code, they must obtain an ODS Code to identify themselves prior to completing the other pre-requisite activities below. If they already have an ODS code, the Customer should check that they are valid for each site they wish to have a migrated HSCN connection installed. | ODS Codes can be requested or verified via the customer's named contact (OC1) if they have one (Health organisations) or by contacting the ODS Team. Further information on ODS Codes and contacts can be found on the NHS Digital website: https://digital.nhs.uk/organisation-data-service/our-services#code allocation.
| PO03 | Connection Agreement | The Customer must obtain a valid Connection Agreement prior to connecting to HSCN. CNSPs are able to check for the existence of a Connection Agreement on the Connection Agreement Portal (https://crm.digital.nhs.uk/hscnconnectionagreementsearch/) prior to processing a new order so the customer should obtain one as soon as possible (once an ODS code has been obtained as per PO02). | Further information on the HSCN Connection Agreement and how to obtain one can be found on the NHS Digital website: https://digital.nhs.uk/services/health-and-social-care-network/new-to-hscn/connecting-to-hscn
| PO04 | Pre-existing Inventory Information | If the Customer wishes to confirm which legacy HSCN services they are using, they should contact their legacy CNSP service provider. | Legacy CNSP service provider should be contacted for further details.
| PO05 | Business Approval Governance | Prior to ordering, the Customer may need business approval for purchasing replacement HSCN services. They should validate this within their organisation and make preparations to ensure they can complete any necessary governance steps. | Customer should consult their organisation to confirm business approval governance that they are required to comply with. Schedule this to occur between contract award and call-off to avoid delays.
| PO06 | Clinical Safety Assessment | Customer should consider their current status of clinical safety assessment ahead of migrating from one CNSP to another on HSCN. This should be initiated now as it may take some time but only needs to be completed ahead of migration (it should not delay placing an order). | Please see the NHS Digital website for further information: https://digital.nhs.uk/services/clinical-safety
| PO07 | National Application Requirements | Customer should consider their current access requirements for all national applications (as well as other applications) as these may be affected by the move from one CNSP to another on HSCN. | Customer should consult their organisation to confirm application usage. Once known, this should be shared with their new CNSP who can advise accordingly (as per OC06 below).
| PO08 | Site and Escalation Contacts | Customer should consider who the correct points of contact are for the new CNSP to engage with when receiving orders and planning site installations. This should include an escalation contact if these primary contacts are uncontactable to avoid delay. This information is needed by the new CNSP to process orders promptly and avoid unnecessary delay. | Customer should consult their organisation to confirm who the best points of contact are to confirm order requirements, provide site details/organise site visits and act as a point of escalations.
| PO09 | Existing HSCN Site Contact | Customer should check that the legacy HSCN site contact details remain accurate. During the CNSP to CNSP HSCN migration and cease processes, key communications are sent to the HSCN site contact. | Customer should contact their legacy and new CNSP service providers by sending an email to confirm the new site contact details, with the following information: - Service Reference (SR) - Site name - New contact Name / Contact Number / E-mail address
| Ref | Item | Description of requirement | Guidance to Customer
Ordering | Ordering
| OR01 | Order Pre-Requisite Information | Customer should collate the following information prior to placing an order for a circuit with the new CNSP. This information is needed by the new CNSP to process the order. | Collate the following standard information as well as additional information required by Customer's CNSP: - Organisation ODS Code - Unique Site ID (ODS site code) - Service Reference - Subnet(s) to be migrated (if appropriate) - Site Name - Full Postal Address - Postcode - Primary' organisation - Site Contact Names (1, 2 etc) - Site Contact Numbers - Site Contact Emails - Technical Contact Name - Technical Contact Number - Technical Contact email - Comms room location (where routers and circuit terminating equipment will be located) - Number of free ‘U’ in the rack(s). - Number of free power outlets for the rack(s) - Room Number - Floor - Building Name - Duct location and state or repair - Way Leave Notice (for any work on private land) If the customer has an intended location for new equipment: - Cabinet / Rack (optional) - Tile (optional) - Rack Position (optional) For site survey visits (as per PI02 and PRM02): - Site points of contact - Parking facilities
| OR02 | Complete Order Form | Customer should complete and check the order form (specific to the chosen procurement route) for information needed to prepare in advance. It is important this is completed promptly to ensure the order progresses. | Order forms should be submitted by the appropriate route for the procurement.
| OR03 | IP Address Retention Request | All Customers must register their IP addresses on the NHS Digital portal prior to connecting or migrating to HSCN. This is required for customers who require new IP addresses and those wishing to migrate their existing IP addresses. If a customer has a private address in the 10 or 172 range they can choose to migrate that address to their new supplier or request a new range and return their existing allocation to the pool. Both options can be done via the portal. If they have a RIPE address that has been allocated by the NHS, these are split into subnets and ring-fenced for suppliers so their existing allocation must be returned to the pool and a new allocation requested, which will be supplied from their new supplier's ring-fenced range. | All HSCN Customers are obliged to follow this process. This should be completed only after they have chosen a new HSCN CNSP: 1. Please request access to the HSCN portal via enquiries@nhsdigital.nhs.uk. 2. Ensure that the Customer requests 'IPAM delegate' permissions under their parent ODS code (e.g. Trust or CCG level) and not site codes (e.g. Trust site or GP practice). 3. Complete an IPAM form via the HSCN portal.
| OR04 | Pre-existing Configuration Information | If the Customer requires router configuration data, it should be requested by contacting the legacy CNSP. Note that Customer's new CNSP will be able to obtain this information at a later date if required. | Customer should contact their legacy HSCN CNSP service provider for further details
| OR05 | National Application Access | Customer should notify their new CNSP if their organisation accesses any Regional or National applications. If they are migrating from a legacy connection and choose to retain their IP addresses, this access should be unaffected. | Customer should inform their new CNSP of the application used at each site so they can advise accordingly. If necessary, they will notify NHS Digital of new IP ranges to ensure they are configured for National Application access.
| Ref | Item | Description of requirement | Guidance to Customer
Pre-Installation | Pre-Installation
| PI01 | Schedule | Customer should discuss and agree with their legacy and new CNSPs, the dates for installation, commissioning and migration of services onto the new HSCN CNSP's network. Migrations should be booked as far in advance as possible to ensure both CNSPs are able to book a slot at an appropriate date and time (in standard hours, unless otherwise agreed). Standard exit provisions guidance (subject to local contract provisions) should be observed. | The Customer should initiate contact with the legacy CNSP and consult with the new CNSP to develop an implementation and migration approach and plan.
| PI02 | Building Access | Customer should ensure that any site or building access requirements are known and organised in advance. Site visits may be required to: - Perform site surveys; - Complete the installation; and - Perform the migration. | Customer should consult with their legacy and new CNSPs to confirm what access they will require, when and agree it with their facilities management/site contacts as appropriate. This should include: - Checking if there are any site or building access restrictions (advanced notice, opening hours etc.); and - Checking if an escort for the legacy and new CNSP's technical engineers is required and available.
| PI03 | Works Risk Assessment | Customer should check if a Risk Assessment and Method Statement (RAMS) is required for surveys and work on site and whether this has been completed. | Customer should confirm within their organisation if any work permits and/or Risk Assessment and Method Statements are required. If so, facilitate the completion and return of them to their new CNSP.
| PI04 | Hardware & Rack Space | Customer should confirm with their new CNSP what hardware will be provided and how it should be installed. This includes confirming what rack space is needed. | Customer should consult with their new CNSP with regard to hardware installation requirements. This should include confirming with their suppliers: - The proposed Customer Premise Equipment (CPE) hardware; - How much rack space is required (number of units/'U'); - Termination; - Cooling requirements; - Connectivity requirements (including Failover); and - Will Network Termination Equipment (NTE) be rack mounted or terminated on wall and whether this needs to be co-Located with CPE. Note: Sufficient space will be needed for the new and existing equipment to be connected and powered-on simultaneously.
| PI05 | Power | Customer should confirm with their new CNSP as to what power requirements are needed. | Customer should consult their new CNSP to check power installation requirements. This should include: - Confirm how many power sockets are required; - Check sufficient power sockets are available near the installation location; - Confirm what type of power connection is required (such as UK standard mains plug or kettle lead); and - If sufficient power or space is not available, arrange for this to be provisioned before the CNSP to CNSP HSCN installation date. Note: Existing CPE will need to be powered-on and connected until the Customer issues notice and the cease is processed so it can be securely wiped/uninstalled (see POMO2 below).
| PI06 | Cables | Customer should check with the new CNSP what cables (RJ45/Fibre) are required for installation. In the case of Fibre cables it is crucial to understand the if multi-mode or single-mode fibre cables are required and that the correct lengths are ordered. The Consumer/Customer should check whether or not the new CNSP will provide these cables/patch leads as part of the installation. | Customer should liaise with their new CNSP to confirm what cabling is required and whether or not the new CNSP will provide these cables/patch leads as part of the installation. Obtain this in advance of the installation and/or migration as required. Ensure any cabling is stored in a location that will be accessible during the installation and migration as required.
| PI07 | Ports/Optics | If the new CNSP HSCN router is connecting into customer's LAN, the Customer should ensure they have sufficient RJ45 or Fibre optic interfaces available. In the case of fibre, the Customer should ensure that they have the correct optical gbics/sfp's in place. | Customer should liaise with their new CNSP to confirm what ports/optics are required and check availability of these on their local network devices.
| PI08 | Firewalls | If the Customer manages their own firewalls, they should consider any firewall or related software changes that would be required as they install and transfer to a new service. | Customer should liaise with their new CNSP to confirm any firewall or software changes that are required.
| PI09 | Test | Customer should create a test plan to include a list of migrated services they need to test as part of the CNSP to CNSP HSCN migration process and allocate resources that will perform these tests. They should perform testing pre-migration, (to test local connectivity to the new HSCN service (using test IP's where appropriate) and during migration (to test they can access all required services). Testing should include (as a minimum) testing access to the internet services, access to email and access to all national and regional application services that are used. It is important that testing is thorough to increase the likelihood of issues being detected early. | Customer should liaise within their organisation to understand which business applications are used at each site and develop an associated test plan.
| PI10 | Change Management | Customer should plan the local activities that need to take place prior to CNSP to CNSP HSCN migration, such as arranging for approval at a local change control board. | Customer should liaise with their change management function to confirm any approval that needs to be obtained. Plan the migration to avoid change freezes and any major release cycles.
| Ref | Item | Description of requirement | Guidance to Customer
Pre-Migration | Pre-Migration
| PRM01 | Risk Assessment | Customer should ensure any risk assessments required by their organisation are completed prior to migration. This should include concluding any Clinical Safety Assessments (as per PO06). | Customer should consult their organisation to confirm risk assessments that may need to be completed.
| PRM02 | Building Access | Customer should ensure access and an escort for the new HSCN CNSP supplier's engineer/s is available on the commissioning date (when the new CNSP installs their managed routers, firewalls and tests the service). | Customer should liaise with their new CNSP to confirm access requirements and agree this with their facilities management/site contacts as appropriate (subject to their organisation's Security Policy). It is strongly recommended that a responsible person on site is tasked with contacting the new CNSP when the carrier engineer arrives to install the circuits. This is to ensure the new CNSP confirms with the attending engineer the exact location for the circuit.
| PRM03 | Migration Process | Customer should ensure that they have planned and agreed migration readiness steps within their organisation in addition to their legacy and new HSCN CNSPs. This should include when the migration slot will occur, when the network will be unavailable, when to move connections to the new CNSP HSCN service, what is the agreed acceptance criteria and what to do if something goes wrong in addition to other activities that their users may need to perform. Subject to local contract provisions, a 2 hour migration window/slot has been used as a 'standard' acceptable migration window before instigation of roll-back or fix forward, however this should be agreed and understood by all parties (customer/legacy/new CNSPs) at this stage. A typical implementation plan may include the phases: site survey (if required); cable installation (if required); router delivery; commissioning of service; pre migration; and migration. If a customer has procured their service via the Dynamic Purchasing Service (DPS) RM3825, there are specific go-live and service stability milestones that the new CNSP should meet. | Customer should consult their legacy and new HSCN CNSPs for full details on the migration. The new CNSP should lead on sequencing events but in agreement with all parties. For further information on DPS RM3825 milestones, please see Customer Call Off Order Form and Terms (specifically M1: Go-Live and M2: Service Stability sections).
| PRM04 | Circuit Handover | Customer should check that the new HSCN CNSP supplier completes their commissioning testing including a failover test (if a resilient service) and provides them with a commissioning test report. | Customer should consult their new CNSP to verify testing has been completed at the point of circuit handover.
| PRM05 | Pre-Migration Testing | Customer should conduct pre-migration testing as defined during the test plan (developed at PI09). This should include local testing of the new HSCN service prior to migration. | Customer should liaise with their new CNSP and business users to develop a comprehensive test plan. Customer is advised to perform testing of the new service as per their developed test plan(s). It is vital that testing is thorough to avoid issues impacting business critical or clinical services.
| PRM06 | Communications (Details known) | Customer should ensure they have contact details agreed with their legacy and new HSCN CNSPs so all parties know who to communicate with during the migration process. This should have been organised in advance but check they are all documented and known at this point. | Customer should consult with both their legacy and new CNSPs to confirm contact details and circulate these within their organisation as appropriate.
| PRM07 | Routing Updates | The new CNSP is able to request a redacted copy of the existing router configuration. They may wish to discuss the current routes to identify if any are no longer required or should be updated. This will enable them to prepare the new configuration for the new router. | Customer should consult with their new CNSP to confirm if router updates are required.
| PRM08 | Submit Cease Request | If the Customer has a complex service that is still in term, a cease quote may need to be provided by their legacy CNSP which can take some time to attain. Whilst the cease order should be requested post migration (see POM03 below), the quote can be requested prior to the migration to reduce delays that may result in prolonged billing. | Customer is advised to request a cease quote via their legacy CNSP's normal communications channel/point of contact.
| PRM09 | Keep Customer Informed (KCI) Emails | As part of the CNSP to CNSP migration scheduling process, Customer may receive 'Keep Customer Informed' (KCI) email notifications or similar from the new CNSP. If so, it is vital that these are checked to confirm that migrations have been scheduled for the correct site (including Service Reference (SR), customer name and ODS) and at the agreed date and time. | Where appropriate, please review KCI emails to confirm they are accurate. If there are any issues, please consult the CNSP promptly.
| PRM10 | Emergency Preparedness, Resilience and Response (EPRR) | During the CNSP to CNSP migration process, it is strongly encouraged that there are close links forged between the Trust IT and EPRR colleagues, to ensure that local risks are identified and mitigated where possible, ideally within a contingency plan, which should be shared with the relevant NHS England & NHS Improvement (London) geographic EPRR patch team in advance. Please also ensure that the Customer includes contact with NHS01 in their plans – to ensure that there is strategic input to the trust go/no-go decision just prior to migration | At a minimum, the Customer should ensure that their internal EPRR Planner is notified of their intent to migrate as early as possible (they should then update the EPRR regional teams). EPRR should be invited to any go/no go calls – as they may have the most up to date knowledge as to a reason why an organisation should not risk being off line. Lines of contact escalation should be established to ensure that, if the migration doesn’t go as planned, EPRR teams are notified that the site is at risk of not being available. Further information can be found on the NHS England website: https://www.england.nhs.uk/ourwork/eprr/
| Ref | Item | Description of requirement | Guidance to Customer
Migration | Migration
| MI01 | Resourcing Available | Customer should check all resource, including onsite access and those involved in the CNSP to CNSP migration process and testing, are available. This should include confirming if someone is needed onsite to perform a roll back if issues are encountered during or post the migration process. | N/A
| MI02 | Communications (Available) | Customer should ensure they have access to any points of contact or management control bridges (conference calls) at the start of the CNSP to CNSP migration window to confirm they are reachable. | N/A
| MI03 | Cabling | Customer should ensure cabling is available to connect new router devices to the network. | N/A
| MI04 | Migration Activities | Customer should follow the CNSP to CNSP migration steps and instructions provided by their legacy and new HSCN CNSPs to complete any activities they are required to perform. It is vital that they don't perform actions (such as unplugging devices) until instructed to do so. | N/A
| MI05 | Testing | Customer should complete testing of all applications and services to ensure they are operating as per design and meet their success criteria as per the test plan (developed at PI09). As described during PRM05, testing should include as a minimum testing access to the internet, access to email and access to all national and regional application services that are used, prior to declaring the CNSP to CNSP migration a success. | N/A
| MI06 | Rollback | Customer should make sure they know what to do if any issues are experienced post completion of the CNSP to CNSP migration process and who to report issues to, within both the legacy and new CNSPs, including how or when rollback would be appropriate. | N/A
| Ref | Item | Description of requirement | Guidance to Customer
Post Migration | Post-Migration
| POM01 | Operational Procedures | Customer should ensure their local operational procedures are updated to reflect their new HSCN CNSP supplier. This should include changing Service Desk contacts for staff in the event they experience network connectivity issues. It may also include updates to: Contract Management; Asset Management; Service Management (service levels); Disaster Recovery/Business Continuity; and Security. | Customer is advised to consult their new CNSP and operational management teams. This activity should be covered during the handover to live service.
| POM02 | Cessation | Once the new HSCN services are operational and the CNSP to CNSP migration process has completed successfully, the Customer should raise a cease notice with their legacy HSCN CNSP to terminate all migrated legacy services. This should not be initiated before the CNSP to CNSP migration process has successfully been completed but soon after this point to avoid unnecessary dual running costs. | Customer should submit a cease request to their legacy CNSP for all migrated services previously provided, once CNSP to CNSP migration has been successfully completed, using the relevant cease process as advised.
| POM03 | Legacy Customer Premise Equipment (CPE) | Customer should not switch-off old equipment (including routers) until instructed to do so by their legacy HSCN CNSP as part of the cease process. They may require access to securely wipe the device or other activities as they advise. This is particularly important if the Customer wants to retain the option of roll-back for a short-period of time. | Please leave old routers and other equipment powered-on until the legacy CNSP advises they can be powered-off during the cease process.
| POM04 | IP Address Management | Once the new CNSP HSCN service is operational, the Customer should confirm that the IP addresses that they are using are held by the NHS Digital IP Address Management (IPAM) team. | Please contact the NHS Digital IP Address Management (IPAM) team (ipamteam@nhs.net) . Further information can be found on the HSCN website: https://digital.nhs.uk/health-social-care-network/technical-guidance/IP-address-management
| POM05 | New Customer Premise Equipment (CPE) Data Feeds | Once the new CNSP HSCN service is operational, the CNSP should ensure that the correct Customer Premise Equipment (CPE) data is being sent to the NHS Digital Network Analytics Service (NAS). | CNSP should ensure that IPFix data is being sent to NAS.