## Title sheet
Known Issues
An extract of all Known Issues recorded against the ITK Workbench
Copyright © 2016, Health and Social Care Information Centre. All Rights Reserved.

## export
# | Status | Priority | Subject | Target version | Created | Found in Version
2148 | New | Normal | Validation fails for ITK 2.2 Acknowledgement Files with Unrecognised service: urn:nhs-itk:services:201005:sendDistEnvelope | Known Issue | 2016-05-27 11:21 | SVN620
2141 | New | Normal | TOC Message Validation Report. Rendering link does NOT work correctly. | Known Issue | 2016-05-24 09:35 | SVN613
2132 | New | Normal | TOC Nullify Document CDAConformanceSchema Check Failures | Known Issue | 2016-05-23 11:30 | TKW 604
2127 | Retest : Failed | Normal | Validator issues in SPINE_CPIS_Validationwith sample messages. | Known Issue | 2016-05-20 14:12 | SVN604
2122 | Triaged | Low | Validator issue in sample message for HPEN | Known Issue | 2016-05-20 12:34 | SVN604
2108 | New | Normal | TOC Compositional Grammar Validation - Space at end of item is NOT rejected. | Known Issue | 2016-03-31 13:48 | Please supply
2107 | New | Normal | Contents of code and codesystem differ but validate correctly. | Known Issue | 2016-03-31 09:51 | Please supply
2097 | New | Normal | Can SO_EXHDMU be altered to run only one message instead of two | Next Release | 2016-03-09 15:45 | ITK 4.0 Config SVN: 455
2096 | New | Low | ATM - All positive tests should validate the input message that is transmitted via ATM as per the ATM Tests Tab in the Requirements Spreadsheet | Next Release | 2016-03-09 15:06 | TKWInstaller_SVN564
2095 | New | Low | Client Mode tests can be a mix of passive and active test cases which is potentially confusing for the user | Next Release | 2016-03-03 15:32 | Please supply
2074 | New | Normal | phconvertingschemavalidator failure for 3 ADT message types | Known Issue | 2015-11-09 11:52 | TKW 4.0
2071 | New | Normal | Validation in PDS SMS Provider .config file is not present for the message specific portion of the ITK Response message. |  | 2015-09-24 12:34 | TKW4.0
2070 | New | Normal | MSCA-IG-004 needs updating on the TOM | Next Release | 2015-09-17 13:18 | 3.11
2068 | New | Normal | TKW ATM - DE-INVMPC and DE-INVMCT create the same error file thereby supplier systems will not capture the correct error for both |  | 2015-07-10 10:49 | TKW 4.0
2061 | New | Normal | Correspondence simulator parse payload exception when receiving a urn:nhs-itk:services:201005:SendDocument-v1-0 (Basic Transmission) |  | 2015-05-29 10:09 | TKW 4.0 Drop4
2060 | New | Normal | TMS Transmit folding manifest item in log causing messages to be written to stdout during validation | TKW 4.0 Drop4 | 2015-05-21 11:06 | TKW 4.0 Drop3
2059 | New | Normal | Socket Error in MTH Simulator | TKW 4.0 Drop4 | 2015-05-21 10:50 | TKW 4.0 Drop3
2039 | New | Urgent | ITK Spine Mini Service - Common Client Requirements-v1.0 - MSCA-IG-005 |  | 2015-03-12 14:21 | 1
2037 | New | Normal | TKW example messages - Businessack does not have ack requested |  | 2015-03-11 14:11 | 0.14
2013 | New | Normal | TKW has a reported issue with saxon in java 8 - unverified |  | 2014-12-16 10:43 | v3.12
2012 | New | Urgent | PDS minin service deployment process |  | 2014-12-08 16:12 | 1.1
2008 | New | Urgent | TOM needs updating |  | 2014-11-20 14:48 | 3.1
2007 | New | Urgent | in SCR mini service we need TKW simulator to do a call to check if the ssotoken is valid |  | 2014-11-17 17:14 | Please supply
1981 | Retest | Normal | Requirements spreadsheet macros need to be updated as Queue Collection is now incorrect |  | 2014-11-07 09:47 | 7.4
1952 | In Progress | Normal | Requirements spreadsheet does not fully reflect the changes in the architecture spec |  | 2014-10-15 15:00 | v7.0
1951 | Retest | Normal | Requirements Spreadsheet - When a CDA bundle is selected on RIA, then Routing Receiver and Routing Requester Modules should show as Mandatory | Sprint046 | 2014-10-13 10:16 | 7.4
1950 | Retest | Normal | on requirements spreadsheet - queu collection requirements appear on Requirements Explained tab even though not selected on RIA | V3.13 | 2014-10-13 10:05 | v7.0
1911 | Triaged | High | TRUD pack NHS Interoperability Toolkit Security Requirements Accreditation & Concessions Release - should be removed |  | 2014-09-23 14:59 | Please supply
1824 | Triaged | Immediate | TKW Validation throws incorrect errors when validating a Child Health Data Sharing Messsage | V3.13 | 2014-07-29 13:51 | TKW Installer V3.11
1747 | In Progress | Normal | Release Notes need to include supported MIM Versions | Next Release | 2014-04-17 12:12 | TKW 3.10
1719 | Retest | Low | TKW Installer cannot be used when text size is increased in windows | V3.13 | 2014-03-31 14:10 | 3.1
1698 | Retest : Failed | Normal | HS_HSC_PR_ICSP and HS_HSC_CP_ICSP testcases not displayed as supported Host test in Autotest Manager | V3.13 | 2014-03-11 11:29 | 6.7
1686 | In Progress | High | Schema Validation Failures for three MLLP Example Messages | Backlog-Dormant | 2014-03-06 10:19 | TKW 3.10
1614 | Triaged | Normal | Intermittent failures of AF_ACK_HOST_SEND_IA due to a timestamp mismatch (differing by 1 second). | Known Issue | 2014-01-30 14:47 | TKW 3.9.4
1601 | Triaged | Normal | SOAPFault - processing in TKW and documentation needs investigation | Backlog-Current | 2014-01-22 15:01 | 3.09
1595 | Retest : Failed | Normal | REF #1601-Simulator Issue - For Test SO_RPLYTO_PH - ADT Synch - when run in ATM, response is http 500 which is correct but the Action is incorrect | Backlog-Current | 2014-01-15 15:32 | Please supply
1575 | In Progress | Normal | REF #1601-Simulator Issue - For Test SO_AANRPL_PH in ATM, Simulator returns an invalid soap action for Asynch_PH message with an anonymous ReplyTo element | Backlog-Current | 2013-12-24 10:00 | TKW Installer 3.9
1573 | Triaged | Normal | REF #1601-Simulator Issue - For Test SO_AANRPL in ATM, Simulator does not reject an Asynch message with an anonymous ReplyTo element | Backlog-Current | 2013-12-19 11:59 | TKW Installer 3.7
1572 | In Progress | Normal | REF #1601-Simulator Issue - For Test SO_ANORPL in ATM, Simulator does not reject an Asynch message with no ReplyTo element | Backlog-Current | 2013-12-19 11:55 | TKW Installer 3.7
1486 | Triaged | High | Copy Recipient Example Messages - Analysis to determine if they hold the correct Recipient Information | V3.13 | 2013-10-23 09:37 | TKW Installer 3.7
1406 | Triaged | Normal | Example Message - SendDocument-v1-0_PDFpayload_DIST_SOAP.xml - is not correct | V3.13 | 2013-09-26 15:12 | 3.7.6
1390 | Triaged | Normal | When Stop on Fail is set a validation is done even when the step before fails | V3.13 | 2013-09-24 09:20 | 3.7_5
1380 | Triaged | Normal | Autotest Manager - Include support for ER_INVXML test in ATM Host Tests | Backlog-Dormant | 2013-09-19 11:55 | TKW Installer 3.7
1379 | Triaged | Normal | Autotest Manager - Include support for ER_INVTIM test in ATM | Backlog-Dormant | 2013-09-19 11:52 | TKW Installer 3.7
1348 | Triaged | Normal | Autotest in client mode should contain a 'Check' on the Test Results Log to remind the tester to check the rendered image on the validation report | V3.13 | 2013-09-16 15:57 | 3.7_3
1244 | Triaged | Low | ATM and Spreadsheet - Add a new Testcase for Asynch to result in HTTP 202 followed by a Post Fault Response | Backlog-Dormant | 2013-08-22 12:43 | TKW Installer 3.6
1242 | Triaged | Low | ATM - Include and indicator in ATM that states that Test pre-reqs are needed prior to Test Execution | Backlog-Dormant | 2013-08-22 11:13 | TKW Installer 3.6.5
1220 | Triaged | Low | Named Simulator Syntax for TKW Autotest Manager | Backlog-Dormant | 2013-08-20 13:37 | TKW Installer 3.6
1130 | Triaged | High | All the NHS Numbers in the TKW Sample Messages should pass Modulus 11 Check | V3.13 | 2013-07-22 10:39 | TKW Installer 3.6
1068 | Triaged | High | ADT Async Response Messages are being returned from simulator with a signature | V3.13 | 2013-07-09 14:49 | TKW Installer 3.6
977 | Triaged | Normal | Autotest Manager - Include a new test for Asynchronous Fault Response | V3.13 | 2013-06-20 15:10 | TKW Installer 3.6
847 | Triaged | High | WITH_PROPERTYSET fails to honour SET tks.transmitter.includesigner Y | V3.13 | 2013-04-16 15:40 | TKWInstaller 3.5
769 | Triaged | Normal | New Schematron Check to pick up multiple and repetitive namespace declarations | Next Release | 2013-03-07 17:09 | TKW 3.5
764 | Triaged | Normal | Autotest Manager - Enhancements to include option to send different levels of CDA documents | V3.13 | 2013-03-05 10:50 | TKW 3.5
748 | Triaged | High | send a business ack and infrastructure ack to two different destinations - supplier raised | Backlog-Dormant | 2013-02-25 13:42 | 3.5
720 | In Progress | High | validation does not pick up invalid to on sync message | Backlog-Current | 2013-02-19 14:12 | 3.5
371 | Triaged | Immediate | TKW Sender.class does not check or report on failure responses in SendDirect() | V3.13 | 2012-11-23 09:55 | TKW Installer v3.3
356 | Triaged | Immediate | SUGGESTION: TKW isnt logging all the things which are reported in the standard output and | V3.13 | 2012-11-20 16:18 | Rev: 16
239 | Triaged | Low | Re-serialisation of transformation enabling CDA validation via SAX. | Backlog-Dormant | 2012-11-06 11:09 | TKW Installer v3.2
216 | Triaged | Low | Cosmetic Differences in TKW installer dialog running on Ubuntu jre1.6.0_37 | Backlog-Dormant | 2012-11-06 09:10 | TKWInstallerv3.3