## Cover Page
Generic Clinical Safety Hazard Log for Connecting Systems - National Care Records Service (NCRS)
Programme | Platforms
Sub-Prog / Project | National Care Records Service
Prog. Director | Stephen Koch | Status | Published
Owner | Dr Rob Jeeves | Version | 1.1
Author | Shelley Johnston | Version Date | 2025-07-22
Generic Clinical Safety Hazard Log for Connecting Systems - National Care Records Service (NCRS)
Important - please read It is expected from the manufacturers of the Connecting Systems and Health and Social Care Organisations that they will integrate the hazards and causes included within this document into their own hazard logs and clinical safety cases and consider where additional controls need to be applied to safely mitigate the clinical risks. In the hazard log that follows, the causes have been categorised into two groups: The first group of causes have been greyed out and marked for awareness - we do not expect third parties to include these in their own clinical risk assessment because third parties cannot further mitigate these specific causes. However, these are included for awareness and they can support an understanding of the limitations of the product. The second group of causes have not been greyed out - we expect third parties to include these in their own clinical risk assessment and consider applying further mitigations to these specific causes. Some of these causes have been partially mitigated by NHS England but require further mitigations by third parties.

## Version History
Amendment History
Version | Date | Amendment History
0.1 | 2023-02-02 | First draft Hazard Log in new format (transcribed from Spine Hazard Log v5.0)
0.2 | 2023-02-27 | Updated in relation to CP-IS "Silent Read" functionality (SPINECLI-419)
1.1 | 2025-07-22 | Upflited to inlcude all Feature Partity items from SCRa to NCRS.
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Bruno Tchek |  | Lead Safety Engineer | 22//07/2025 | 1.1
Zak Bickhan |  | Clinical Safety Officer | 22//07/2025 | 1.1
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Dr Rob Jeeves |  | NCRS Clinical Lead / Clinical Safety Officer | 22//07/2025 | 1.1
Distribution
NCRS Integrating Parties
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## Hazard Log
|  | Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status | Comments
No. | Date Added | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
1 | 2023-01-05 | NCRS or a component / feature (e.g. PDS, SCR, NRL, CP-IS, RA, FGM-IS) is not available | User cannot access patient/clinical information at all or in a timely fashion | Inappropriate treatment or delay to care | Denial of access due to configuration of user profile (e.g. RBAC). The system could deny user access to the system if their access permissions are incorrectly configured. | RBAC model clearly identifies what permissions are needed to gain access to the various features available via NCRS (e.g. CP-IS, Reasonable Adjustments, etc.). | [5 empty] | Considerable | Low | 2 | [7 empty] | Considerable | Very Low | 2
[6 empty] | Ensuring that only users with the relevant RBAC permissions (and legitimate relationship) are permitted to view Summary Care Records in NCRS so that patient data remains secure and only patient information necessary for the job role is shared | NCRS-4 NCRS-368 NCRS-376
[6 empty] | Allowing a user with appropriate RBAC controls to access NCRS and all component features. | Login: NCRS-68 CP-IS: NCRS-1093 and NCRS-2559 RA: NCRS-1680 NDOP: NCRS-1245 SCR: NCRS-368 PDS Edit: NCRS-1013 FGM-IS: NCRS-1285 NRL: NCRS-554 | [12 empty] | Communications to national Registration Authority network explaining the appropriate allocation of the new CP-IS Silent Read RBAC Activity Code (B0170) and the existing code (B0107) | To be actioned by CP-IS Programme
[6 empty] | Summary Care Record tab does only show for a user with the correct access | NCRS-249
[6 empty] | Summary Care Record tab does not show for a user without the correct access | NCRS-272
[6 empty] | The RA Flag team have existing controls in places for appropriate access | RAF005
[5 empty] | User has forgotten login credentials (e.g. PIN, Username/Password) and/or authentication devices (e.g. Smartcard, iPad) preventing access to NCRS. |  |  |  |  | Self-service portal for Smartcard unlock / certificate renewal | https://digital.nhs.uk/services/registration-authorities-and-smartcards/register-for-self-service-smartcard-unlock
[5 empty] | The internet network/gateway could become temporarily unavailable. | A message to notify the user of loss of internet connection appears automatically. | NCRS-358 | Training / guidance advising users that they will be unable to return to the patient’s demographics or SCR and perform another search until reconnected to the internet if they navigate back to the search page during loss of internet connection. | Add hyperlink when available
[6 empty] | User can continue to navigate around a patient’s record if internet connection is lost at the time of access (for up to 30 min) so that provision of care to patient is undisrupted. | NCRS-84 NCRS-340
[5 empty] | System and data sources unavailable during app updates: system may be unavailable whilst it is being upgraded from one version to another. Should unforeseen circumstances occur, this period of unavailability could be extended. | Providing an alert service wrap for monitoring activity so that we can respond quickly and effectively to any live issues [NCRS-3] |  | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. | https://digital.nhs.uk/services/national-care-records-service/user-guidance | Any updates required to the system during the pilot period will be communicated and co-ordinated with the relevant pilot sites.
[6 empty] | Monitoring the NCRS product once live to ensure it is not affected by browser updates, etc. [NCRS-26] Any updates required to the system during the pilot period will be communicated and co-ordinated with the relevant pilot sites. |  |  |  | Local and NHS England service monitoring; If there are issues in any interface, alerting is in place that inform the support team.
[5 empty] | Third-party software could interfere with the application or obscure some of the data on the screen. |  |  |  |  | Local and NHS England service monitoring; If there are issues in any interface, alerting is in place that inform the support team.
Individual organisations are responsible for controlling and maintaining users' devices and for assessing the compatibility of installed software.
[5 empty] | (Awareness) Any SCRs uploaded before 6th October 2017 and not updated since cannot be viewed in NCRS. | A one-off process to bulk upload SCRs with Additional Information including the change to include COVID-19 codes in the Inclusion Dataset will update the vast majority (over 50 million patient records) of SCRs. |  | Communication sent to user base to alert on the HTML rendering issue of summaries with the 'Recently registered statement' issue. |  | Weekly review of error logs of events including where SCRs are not able to be rendered.
[6 empty] | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. |  | HCP may be able to access alternative sources of clinical information such as other paper records, clinical hubs or the patients themselves.
[5 empty] | (Awareness) Incompatible NRL messaging structure | The NRL includes a built-in validation system ensuring providers and consumers adherence to specific integration requirements. | NRL Hazard 1, 3, 5, 7 and 10
[6 empty] | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331
[5 empty] | (Awareness) Patient does not consent to advertising that a NRL record exists or advertises the existence of a record but not the content | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331
[5 empty] | (Awareness) IG model inhibits NRL data transfer or no data sharing agreement in place | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331
[5 empty] | (Awareness) Patient having S Flag status will prevent NCRS users viewing the patient's SCR, NRL, RA record and only partial demographics information will be returned | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted.
[5 empty] | (Awareness) Data source/provider fails or refuses to make requested patient data available for retrieval. | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331
[5 empty] | (Awareness) Patient's data sharing preferences are incorrectly applied within NRL (erroneously making too little or too much information available) | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331
[5 empty] | (Awareness) Ineffective NCRS search engine (e.g. error in the validation rules specified for patient search, inappropriate error messages) | Clinical review of validation logic used in patient search. Error message text follows NHS England service manual and GOV.UK design system. | NCRS-502
[5 empty] | (Awareness) Failure of national infrastructure (e.g. Spine) / Patient Flag Service / APIM) | A message to notify the user of loss of internet connection appears automatically. | NCRS-358 | Training / guidance advising users that they will be unable to return to the patient’s demographics or SCR and perform another search until reconnected to the internet if they navigate back to the search page during loss of internet connection. | Add hyperlink when available | Local and NHS England service monitoring; If there are issues in any interface, alerting is in place that inform the support team.
[6 empty] | User can continue to navigate around a patient’s record if internet connection is lost at the time of access (for up to 30 min) so that provision of care to patient is undisrupted. | NCRS-84 NCRS-340 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted.
[6 empty] | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
[6 empty] | Error handling for failed requests to Patient Flag Service. | FLAGSAPI-358
[5 empty] | (Awareness) NCRS fails to return the 'Contact details' and/or 'Document' associated with an NRL pointer | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331
[5 empty] | (Awareness) User is unable to download or print a patient record (e.g. NRL, RA) due to the fact that no generic 'print' function is available in NCRS. | Adding National Reasonable Adjustments record to NCRS | NCRS-969, NCRS-1631
[5 empty] | (Awareness) Strategic authentication solution (currently CIS 2) unavailable which prevents users from authenticating and accessing NCRS |  |  | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. |  | CIS2 is currently a platinum service and support is offered 24/7. The resilience of the service is improved by running a dual service which could be site switched (like Spine offers).
Local and NHS England service monitoring; If there are issues in any interface, alerting is in place that inform the support team.
Clinical System or device is not configured for the Strategic authentication solution (currently CIS2)
[5 empty] | (Awareness) Locum Pharmacist log-on role is unavailable preventing access to NCRS. This would be absolute when this is the only role available to the user or would be relative where more than one role is available. | Adding the unique login process for locum pharmacists using organisation code 'FFFFF' to NCRS | NCRS-970 | Training material is being updated to include locum pharmacists access to NCRS. | Add hyperlink when available | A HCP (locum pharmacist) would still be able to access a patient record using alternative ODS code to the most appropriate one as temporary measure following agreed local processes.
Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted.
[5 empty] | (Awareness) The list of ODS codes returned to the locum pharmacist is unavailable, incomplete or incorrect due to missing ODS codes or technical issue with the product. | Adding the unique login process for locum pharmacists using organisation code 'FFFFF' to NCRS | NCRS-970
[5 empty] | (Awareness) GP system uploads a SCR to Spine that does not follow the agreed text (html) specifications preventing the record from being parsed in NCRS. | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. |  | HCP may be able to access alternative sources of clinical information such as other paper records, clinical hubs or the patients themselves.
Weekly review of error logs of events including where SCRs are not able to be rendered.
Onboarding process for new GP suppliers whereby messages are validated against the specification.
[5 empty] | Incorrect NHS number provided by user | NCRS does ensure validation of NHS numbers provided and issues a message to users if incorrect.
[6 empty] | Displaying a landing page to users which presents with key information and functions relating to their use of the application | NCRS-115
[5 empty] | Invalid NHS number provided by user | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
SPINE does ensure validation of NHS numbers provided and issue a message to users if incorrect.
[5 empty] | (Awareness) Data sources consumed by NCRS are partially implemented / populated; e.g.: Reasonable Adjustments record, CP-IS, COVID-19 Vaccination data, FGM-IS | Local Authorities are required to achieve a minimum of 95% coverage of NHS numbers prior to implementation, process developed to identify any missing NHS numbers and verify demographic details through DBSB service. | ref. CP-IS Hazard 2. | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. | https://digital.nhs.uk/services/national-care-records-service/user-guidance
[6 empty] | Disclaimer text explains that it is possible that the patient may have had COVID-19 vaccination events that are not yet available on NCRS. | NCRS-2011
[6 empty] | The "DPS to Spine Covid Vaccinations & Adverse Reactions Specification" enforces inclusion of all mandatory data items. | https://hscic365.sharepoint.com/:w:/r/sites/NHSDInternalVaccsComms/Shared%20Documents/SCRa/DPS%20to%20Spine%20File%20Specifications/DPS%20to%20Spine%20-%20Covid%20Vaccinations%20%26%20Adverse%20Reactions%20Specification%20v1.0.docx?d=w5a65e4c35e0749b38accd9ab4f1cdb2e&csf=1&web=1&e=7vbqr5
[5 empty] | (Awareness) NCRS is unable to consume different data sources due to differences in technical specifications or conformance from external parties (e.g. NRL). | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. | https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | (Awareness) Data source consumed by NCRS is out of date e.g. NRL, SCR, CP-IS, RA, COVID-19 Vaccination data, FGM-IS | Local Authorities are supplied with a guide for error messages handling around patient demographics matching. | CP-IS Hazard 3. | Staff training in use of CP-IS Safeguarding update requirements: ref. CP-IS Hazard 10.
[6 empty] | Disclaimer text explains that it is possible that the patient may have had COVID-19 vaccination events that are not yet available on NCRS. | NCRS-2011
[6 empty] | Regular automatic upload of Covid Vaccination data from PoC systems to DPS followed by daily automatic upload of this data to Spine at [redacted]. | SPII-32828
[5 empty] | (Awareness) Data source consumed by NCRS (e.g. SCR, NRL, Patient Flag Service) is malformed preventing the record from being displayed in NCRS. | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. | https://digital.nhs.uk/services/national-care-records-service/user-guidance | HCP may be able to access alternative sources of clinical information such as paper/local/regional electronic records, clinical hubs or the patients themselves.
[6 empty] | Providing an alert service wrap for monitoring activity so that NHS England can respond quickly and effectively to any live issues | NCRS-3
[6 empty] | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. | https://digital.nhs.uk/services/national-care-records-service/user-guidance | Weekly review of error logs of events including where SCRs are not able to be rendered.
[6 empty] | Error handling for failed requests to Patient Flag Service. | FLAGSAPI-358 |  |  | Onboarding process for new GP suppliers whereby messages are validated against the specification.
[5 empty] | (Awareness) CP-IS messaging failure or error: uploading of the CP-IS record to Spine | Connection to the CP-IS service is via the Spine Core PDS service and accredited Integrated systems are required to undergo assurance process | ref. CP-IS Hazard 1. | Local Authorities are supplied with a guide for error messages handling around patient demographics matching: ref. CP-IS Hazard 3. |  | CP-IS monitoring at NHS England - live site utilisation reports | CP-IS Hazard 8.
[6 empty] | Local Authorities are supplied with a guide for error messages handling around patient demographics matching. | CP-IS Hazard 3. | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. |  | CP-IS monitoring at NHS England - live site utilisation reports | CP-IS Hazard 8.
[5 empty] | (Awareness) CP-IS local records without a NHS number due to insufficient NHS number coverage: LA records would not be uploaded to Spine without a NHS number. | Local Authorities are required to achieve a minimum of 95% coverage of NHS numbers prior to implementation, process developed to identify any missing NHS numbers and verify demographic details through DBSB service. | ref. CP-IS Hazard 2. | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted.
[6 empty] | Local Authorities are supplied with a guide for error messages handling around patient demographics matching. | CP-IS Hazard 3.
[5 empty] | (Awareness) Delay or time gap between a record or clinical information being made available locally and this being uploaded to Spine (e.g. NRL, SCR, CP-IS, COVID-19 Vaccination data, FGM-IS). | CP-IS monitoring at NHS England - live site utilisation reports. | CP-IS Hazard 8. | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted.
[6 empty] | Enabling the upload Child Protection Orders for any child regardless of whether they are flagged as "Sensitive" on Spine. | SPII-34325
[6 empty] | Disclaimer text explains that it is possible that the patient may have had COVID-19 vaccination events that are not yet available on NCRS. | NCRS-2011
[6 empty] | Regular automatic upload of Covid Vaccination data from PoC systems to DPS followed by daily automatic upload of this data to Spine at [redacted].. | SPII-32828
[5 empty] | The User Role Profile ID (URPID) provided in the 'Deep Link' does not match those provided in the user's profile after authentication | If the URPID provided in the "Deep Link" does not belong to the authenticated user, does not contain activity code B0264, or is otherwise invalid, then the user must select an appropriate role manually in order to be able to access NCRS. If no appropriate role exists then the user will not be able to proceed. | NCRS-2403
[5 empty] | (Awareness) Spine reads or stores one of the parameters supplied in the 'Deep Link' incorrectly | Ensuring that the parameters (i.e. NHS Number, User Role Profile ID (URPID), and ASID) provided in the "Deep Link" are correctly stored and retrieved before and after user authentication | NCRS-2404
[5 empty] | Incorrect/Invalid NHS number provided in "Deep Link" URL | Connecting systems are required to validate NHS Numbers before launching NCRS via the "Deep Link" URL. | NCRS-DL.01
[6 empty] | An error message is displayed in NCRS if an invalid NHS Number is supplied. | NCRS-2404
[5 empty] | Incorrect parameters in "Deep Link" URL i.e. wrong order of parameters, mandatory parameters missing, parameters formatted incorrectly, additional parameters not specified in the developer guidance | NHS Number is the only mandatory parameter and an error message is displayed in NCRS if no NHS Number is supplied. If the URPID is provided then a warning message is displayed to the user who must select a role manually. | NCRS-2404
[5 empty] | Defect in system, data source, or other connecting system | Ensure regular automated regression testing in to the overnight build in order to monitor that the NCRS product, once live, is not affected by browser updates. Daily healthchecks run by TechOps. | NCRS-802 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. | https://digital.nhs.uk/services/national-care-records-service/user-guidance | Providing an alert service wrap in place for monitoring activity so that we can respond quickly and effectively to any live issues. | NCRS-3
[5 empty] | (Awareness) User cannot access features which are not available in NCRS and either interprets their absence incorrectly or makes a decision based on incomplete information | Feature parity between SCRa and NCRS is a strategic objective. | NCRS roadmap | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. The disparity, in terms of functionality, between SCRa and NCRS is highlighted in training materials. | [18 empty] | Closed | Feature Parity for NCRS from SCRa was achieved in 2024.
[5 empty] | (Awareness) NCRS receives an inappropriate error response to a retrieval attempt | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
[5 empty] | (Awareness) Retrieval of specific resources (e.g. NRL, CP-IS, RA, FGM-IS, COVID-19 Vaccinations, SCR) upon retrieval of a patient record by a user takes too long or fails. | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
Spine undergoes regular non-functional testing to ensure that response times are within tolerance.
Spine's response times are continually monitored and TechOps are automatically alerted to any errors/failures.
[5 empty] | (Awareness) Patient does not consent for / opts out of a particular record / resource type (e.g. SCR, Reasonable Adjustments). |  |  |  |  | Where a patient chooses to opt out of / dissent to the creation or subsequent update of a record / resource, the HCP is expected to explain the risks to the patient associated with this decision and to confirm that the patient has capcity to make it before actioning the request.
[5 empty] | System Performance: | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A
[5 empty] | Local hardware performance: hardware is unable to operate at an appropriate speed. | Adopting a mobile responsive framework so that the product scales and displays correctly on a mobile device (buttons need to be easy to locate and click, there should be no horizontal scrolling required) | NCRS-115 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. |  | Local conformance with Warranted Environment Specification (WES) | https://digital.nhs.uk/services/national-care-records-service#implementation
[5 empty] | Internet network/gateway experiencing poor performance, this may result in poor performance of the local system. (For NRL: This include issues relating to a local aggregator e.g. LHCRE /Shared Care Record from a different care setting witness a delay in reaching NRL through national gateway). | NRL programme have control over NRL networking and infrastructure supporting the service. | NRL Hazard 3, 5 and 10 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted.
[6 empty] | CP-IS is supported by the SPINE demographics' network capabilities/resources. | CP-IS Hazard 4
[5 empty] | (Awareness) Volumetric assumptions exceeded: The anticipated volumes of data passing through the Interface could exceed what was anticipated during the design process. | Providing an alert service wrap in place for monitoring activity so that we can respond quickly and effectively to any live issues. | NCRS-3 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. |  | The transfer of COVID-19 Vaccinations data from DPS to Spine Clinicals is done in batches [redacted].
[5 empty] | Local connectivity network (3G, 4G, Wi-Fi) issues specific to NCRS | Establishing a strong, resilient and reliable security model for accessing NCRS via mobile over the internet | NCRS-2 NCRS-137 NCRS-886 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted.
[6 empty] | A message to notify the user of loss of internet connection appears automatically. | NCRS-358 | Training / guidance advising users that they will be unable to return to the patient’s demographics or SCR and perform another search until reconnected to the internet if they navigate back to the search page during loss of internet connection. | Add hyperlink when available
[6 empty] | User can continue to navigate around a patient’s record if internet connection is lost at the time of access (for up to 30 min) so that provision of care to patient is undisrupted. | NCRS-84 NCRS-340
[5 empty] | (Awareness) NRL networking issues with uploading and retrieving patient record | NRL programme have control over NRL networking and infrastructure supporting the service. | NRL Hazard 3, 5 and 10 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted.
2 | 2023-01-05 | Incorrect patient record retrieved | User accesses demographic and clinical information relating to the wrong patient. (This leads to an absence of the correct information and presence of incorrect/misleading information.) | Inappropriate treatment or delay to care | Retrieval: | N/A | N/A | N/A | N/A | N/A | N/A | Major | Medium | 3 |  | N/A | N/A | N/A | N/A | N/A | N/A | Major | Very Low | 2 |  | N/A | N/A | N/A
[5 empty] | (Awareness) Database error / logic where referencing points to wrong clinical record (e.g. NRL, CP-IS, RA, FGM-IS, COVID-19 Vaccinations) | Integrating National Record Locator with NCRS to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 |  |  | Local Business Processes/Procedures, including for CP-IS. | CP-IS Hazard 2.
[6 empty] | Adding Reasonable Adjustments feature to NCRS | NCRS-969, NCRS-1631, FLAGSAPI-135 |  |  | The RA Flag team have existing controls in places for the RA Flag to be associated to the correct/relevant patient. | RAF007, RAF010
[6 empty] | Adding FGM-IS feature to NCRS | FLAGSAPI-147
[6 empty] | The details of related persons (e.g. Next of Kin) are correctly populated within a patient's record. | NCRS-616
[6 empty] | Adding COVID-19 Vaccinations feature to NCRS | NCRS-2658
[6 empty] | Allowing a user with appropriate RBAC to view when a child has CP-IS added to his/her record | NCRS-868, KF-1634 |  |  | NRL programme have a relative control over NRL record published. | NRL Hazard 2, 4, 8 and 9
[5 empty] | User error (i.e. Wrong patient selected) | Patient's demographics (inc. name, DoB, Address) are displayed in a banner at the top of every screen within NCRS to ensure the correct Patient is identified at all times during view. | NCRS-33 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. |  | The postcode search feature is only available to users with activity code B0098. The national RBAC database states that: "This activity must only be allocated to a limited number (3 to 4) of correctly trained demographics staff working in a local back office environment either at a Trust or national level." | NCRS-502
[6 empty] | Search results returned limited to 50 results. This is to avoid the risk of a user picking the wrong patient. Any more than 50 results returned will result in no results being returned. | NCRS-334
[6 empty] | Adopting a mobile responsive framework so that the product scales and displays correctly to the screen size in use (buttons need to be easy to locate and click, there should be no horizontal scrolling required) | NCRS-1
[6 empty] | Enabling the view of any historical data (where it exists) by pressing a button underneath the relevant section | NCRS-89
[5 empty] | (Awareness) Incorrectly entered data in source system (inc. demographics and non end-dated CP-IS records) (e.g. in Local Authority systems, COVID-19 Vaccination PoC systems/DPS) | CP-IS data is loaded to the NHS Spine matched from the Local Authorities data based on PDS Cross Check trace. | CP-IS Hazard 2 and 5. | Local Authorities policy and training around local record keeping, and patient identification and search on health IT systems: ref. CP-IS Hazard 2. |  | Local Business Processes/Procedures, including for CP-IS | CP-IS Hazard 2.
[6 empty] | Adding PDS edit feature to the new NCRS application | NCRS-1011 |  |  | Training / guidance advising users that NHS Number search and basic details search, where surname, date of birth and gender are mandatory, will not find anything other than an exact match, so partial names or D.O.B’s will not return a result.
[10 empty] | Vaccine Data Resolution Service allows patients to request resolution of inaccuracies in their COVID-19 vaccination history. | https://www.nhs.uk/contact-us/vaccine-record-help/
[5 empty] | (Awareness) Incorrect linkage of data from source system through to national record (e.g. misidentification by Local Authority (CP-IS), COVID-19 Vaccination PoC/DPS, NRL) | CP-IS data is loaded to the NHS Spine matched from the Local Authorities data based on PDS Cross Check trace. | CP-IS Hazard 2 and 5.
[6 empty] | Source File in DPS undergoes a Master Patient Service (MPS) trace to verify the details of the patient (NHS number). The list of verified NHS number is sent to Spine via MESH - the confidence threshold applied by MPS is 100%. | Vaccinations Data Assurance Statement_20210201 |  |  | Vaccine Data Resolution Service allows patients to request resolution of inaccuracies in their COVID-19 vaccination history. | https://www.nhs.uk/contact-us/vaccine-record-help/
[6 empty] | NRL programme have a set of controls over NRL records published. | NRL Hazard 2, 4, 8 and 9
[5 empty] | Incorrect/Invalid NHS Number provided in "Deep Link" URL | Connecting systems are required to validate NHS Numbers before launching NCRS via the "Deep Link" URL. | NCRS-DL.01
[6 empty] | An error message is displayed in NCRS if an invalid NHS Number is supplied. | NCRS-2404
Inappropriate creation or editing of a patient demographic or clinical information in NCRS e.g. RA flag and PDS edit
[5 empty] | Searching: | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A
[5 empty] | Missing, incorrect, incomplete search criteria that results in the misidentification of the patient from the demographic information. | Patient data will not be fetched if the patient identity could not be verified at the time of searching/fetching or if NHS Number is not present. | NCRS-334 NCRS-500 NCRS-502 | Training / guidance advising users that NHS Number search and basic details search, where surname, date of birth and gender are mandatory, will not find anything other than an exact match, so partial names or D.O.B’s will not return a result. | https://digital.nhs.uk/services/national-care-records-service/user-guidance
[6 empty] | Form validation ensures that all mandatory search parameters are provided before a search can be performed. | NCRS-334 NCRS-500 NCRS-502
[6 empty] | Patient data will not be fetched if the patient identity could not be verified at the time of searching/fetching or if NHS Number is not present. | NCRS-334 NCRS-500 NCRS-502
[6 empty] | The NCRS search screens mimic previous functionality in SCRa which has been proven in use over a number of years. NCRS includes the following search functionality: - Submit NHS Trace (NHS Number) - Simple Trace (Basic Patient Details) - Advanced Search - Postcode Search | NCRS-334 NCRS-500 NCRS-502
[5 empty] | Incorrect NHS number or patient identifier(s) provided. | Patient's demographics (inc. name, DoB, Address) are displayed in a banner at the top of every screen within NCRS to ensure the correct Patient is identified at all times during view. | NCRS-33 |  |  | Health Care Professionals responsibility to check the Patient Banner information when viewing Electronic Health Care Record.
[6 empty] | Displaying a landing page to users which presents with key information and functions relating to their use of the application | NCRS-115
[5 empty] | Awareness User may erroneously access the patient record of a contact of an index patient (e.g. using 'Copy Contact NHS Number' instead of 'Copy NHS Number') | Only one patient record can be viewed at a time | NCRS-413 |  |  | Health Care Professionals responsibility to check the Patient Banner information when viewing Electronic Health Care Record.
[5 empty] | Awareness Wrong NRL patient record sent to consumer | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
[6 empty] | NRL programme have a set of controls over NRL records published. | NRL Hazard 2, 4, 8 and 9
[5 empty] | Awareness Incompatible NRL messaging structure | The NRL includes a built-in validation system. | NRL Hazard 5
[5 empty] | Awareness NRL Transcription Errors | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
[5 empty] | Awareness Incorrect NHS number entered by NRL pointer provider (could impact 2 patients records) | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
[6 empty] | NRL programme have a set of controls over NRL records published. | NRL Hazard 2, 4, 8 and 9
[5 empty] | Awareness Information sent to NCRS from Spine or from external data sources (e.g. NRL, Patient Flag Service) includes information from the wrong patient record. | Enabling “Patient Search” in NCRS so that the end user can view a patient’s summary care record | NCRS-54
[6 empty] | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
[6 empty] | Ensuring that responses (to Reasonable Adjustments and FGM-IS requests) are for the expected patient | FLAGSAPI-135, FLAGSAPI-147
[6 empty] | NRL programme have a set of controls over NRL records published. | NRL Hazard 2, 4, 8 and 9
[5 empty] | Awareness Following the link for 'View document' (NRL), the user is taken to the wrong document for that particular patient or a document pertaining to an unrelated patient | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive | NCRS-435
[5 empty] | Duplicate patient records (PDS or local patient records) exist |  |  |  |  | Potential duplicate records are automatically flagged to the National Back Office (NBO) who deal with duplicate and confused records. | https://digital.nhs.uk/services/national-back-office-for-the-personal-demographics-service#what-we-do
[5 empty] | Awareness Integrated local system caches an incorrect locally stored copy of a patient's Reasonable Adjustments record. | The RA Flag team have existing controls in places for the RA Flag to be associated to the correct/relevant patient. | RAF007, RAF010
[5 empty] | User of third party clinical systems may have multiple different records open at once i.e. Patient A record open in third party clinical system and Patient B record opens in NCRS. Note: see additional controls for further details regarding mitigation. | Patient's demographics (inc. name, DoB, Address) are displayed in a banner at the top of every screen within NCRS to ensure the correct Patient is identified at all times during view. | NCRS-33 |  |  | Health Care Professionals responsibility to check the Patient Banner information when viewing Electronic Health Care Record. | [5 empty] | Onboarding organisation will receive the NCRS Integration Supplier Test Scripts. Test 21: For systems which support multiple instances covers this: Retreive Patient 1 in the calling application. Access NCRS from the calling application and view patient NCRS record. Start another instance of the calling application Retreive Patient 2 in the calling application. Access NCRS from the calling application and view patient 2 NCRS record Expected result: NCRS button is present and active. Patient 1's NCRS record can be viewed. When the 2nd instance of the calling application is launched and Patient 2's NCRS record is accessed, the NCRS record for patient 1 becomes inaccessible.
[5 empty] | User retrieves Patient A in NCRS via "Deep Link" and then navigates to Patient B within NCRS leaving Patient A retrieved in the calling application. | Patient's demographics (inc. name, DoB, Address) are displayed in a banner at the top of every screen within NCRS to ensure the correct Patient is identified at all times during view. | NCRS-33 |  |  | Health Care Professionals responsibility to check the Patient Banner information when viewing Electronic Health Care Record.
[5 empty] | Awareness User attempts to use NCRS in multiple browser tabs e.g. by launching NCRS via the "Deep Link" URL for different patients within a third party clinical system | NCRS can only be used in one browser window/tab at a time. A warning message is displayed in the original window/tab and the content is disabled if NCRS is subsequently launched in a new window/tab. | NCRS-413 |  |  | Health Care Professionals responsibility to check the Patient Banner information when viewing Electronic Health Care Record.
3 | 2023-01-05 | Information presented in an incorrect, incomplete, or confusing manner or is overlooked | User misinterprets or does not notice relevant clinical information about the patient | Inappropriate treatment or delay to care | Awareness NCRS presents the clinical information in a confusing manner | The design approach takes into account the extensive users research to ensure NCRS is intuitive and easy to use. NCRS follows the NHS.UK design guidelines to support a consistent user experience. |  | Training highlights where there is a difference between NCRS and legacy SCRa. | https://digital.nhs.uk/services/national-care-records-service/user-guidance |  |  | Major | Medium | 3 | N/A | The design takes into account ongoing extensive user research to ensure NCRS is optimised to be intuitive and easy to use. NCRS incidents are reviewed to consider where improvements can be made to the NCRS user interface. | [5 empty] | Major | Very Low | 2
[5 empty] | User error (oversight / not selecting), inappropriate use, untrained user, local business processes not followed (actions not taken by users following the information presented to them). | The design approach takes into account the extensive users research to ensure NCRS is intuitive and easy to use. NCRS follows the NHS.UK design guidelines to support a consistent user experience. |  | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance | [6 empty] | The design takes into account ongoing extensive user research to ensure NCRS is optimised to be intuitive and easy to use. NCRS incidents are reviewed to consider where improvements can be made to the NCRS user interface.
[5 empty] | Awareness The display of a record consumed by NCRS (e.g. Reasonable Adjustments, SCR) is malformed e.g. rendering issues when multiple data items are present or long supporting comments are provided | Preventing the display of SCRs uploaded before 6th October 2017 so that the end user does not misinterpret information that may not render properly in NCRS due to the 'static' html. Message: “This Summary Care Record is not available to view as it will not display correctly”. | NCRS-88
[6 empty] | Adding Reasonable Adjustments feature to NCRS | NCRS-969, NCRS-1631, FLAGSAPI-135
[6 empty] | Reasonable Adjustments are always displayed above underlying conditions when viewing a Reasonable Adjustments record | NCRS-2423
[5 empty] | User difficulty in navigating around NCRS | The design approach takes into account the extensive users research to ensure NCRS is intuitive and easy to use. NCRS follows the NHS.UK design guidelines to support a consistent user experience. |  |  |  | Addressing user feedback is an ongoing priority for the NCRS development team. Feedback received via various channels is prioritised for development with input from Live Services. | https://nhsd-confluence.digital.nhs.uk/display/CLP/Simplified+view+of+priorities |  |  |  |  | The design takes into account ongoing extensive user research to ensure NCRS is optimised to be intuitive and easy to use. NCRS incidents are reviewed to consider where improvements can be made to the NCRS user interface.
[6 empty] | Adopting a mobile responsive framework so that the product scales and displays correctly on a mobile device as well as on desktops - essentially, the product can scale to any screen size and orientation (buttons need to be easy to locate and click, there should be no horizontal scrolling required) | NCRS-1
[6 empty] | Ensuring end user can continue to navigate (back button) around the patient’s record whilst internet connection is lost at the time of access so that provision of care to patient is undisrupted. | NCRS-84 NCRS-340
[6 empty] | Ensuring the system is able to handle an error or failure scenario in a user journey within NCRS and the user is displayed an informative error in order to ensure the system is usable and intuitive. | NCRS-435
[6 empty] | Addressing user feedback is an ongoing priority for the NCRS development team. Feedback received via various channels is prioritised for development with input from Live Services. | https://nhsd-confluence.digital.nhs.uk/display/CLP/Simplified+view+of+priorities
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | Awareness Possibility of a word being truncated without being hyphenated leading to user misinterpreting the information. | Adding 'hyphen' to indicate to the user that there is a line break in the middle of a work to avoid misinterpretation of clinical information. | NCRS-824
[6 empty] | Adopting a mobile responsive framework so that the product scales and displays correctly on a mobile device as well as on desktops - essentially, the product can scale to any screen size and orientation (buttons need to be easy to locate and click, there should be no horizontal scrolling required) | NCRS-1
[5 empty] | Awareness Floating 'Return to top' button or demographics (Name & DoB) tile may obscure or overlap other information presented on the screen. This cause pertains to all device types used to access NCRS but is more pertinent to mobile users. | THE USER WILL BE ABLE TO SCROLL UP AND DOWN TO REVEAL ANY CLINICAL INFORMATION THAT MAY BE OBSCURED BY THE 'RETURN TO TOP' AND 'FLOATING BANNER'. NO CLINICAL INFORMATION WILL BE PERMANENTLY OBSCURED.
[5 empty] | Awareness The NRL information viewed by the clinician may not contain accurate patient information. | NRL programme have minimum control over record standards published via NRL: ref. NRL Hazard 1, 2, 4, 7, 9, 10 and 11 |  | NRL Guidance issued to users of NCRS and included in the business change resources.
[5 empty] | Awareness The NRL information viewed by the clinician is out of date and/or does not align with current best practice. | NRL programme have minimum control over record standards published via NRL: ref. NRL Hazard 1, 2, 4, 7, 9, 10 and 11 |  | NRL Guidance issued to users of NCRS and included in the business change resources.
[5 empty] | Awareness Conflicting NRL data structure (e.g. different abbreviations), data formats and languages used (e.g. pointers and documents detail) across different healthcare settings. | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | NRL Guidance issued to users of NCRS and included in the business change resources.
[5 empty] | Awareness NRL Indexing data presentational issues | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | NRL Guidance issued to users of NCRS and included in the business change resources.
[6 empty] | NRL programme have a set of controls over NRL record published. | NRL Hazard 2, 4, 5, 6, 7, 8, 9 and 10
[5 empty] | Awareness Modification to the NRL pointer model | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | NRL Guidance issued to users of NCRS and included in the business change resources.
[5 empty] | Awareness Patient having S Flag status will prevent NCRS users viewing the patient's complete record. | Enabling the upload Child Protection Orders for any child regardless of whether they are flagged as "Sensitive" on Spine. | SPII-34325
[5 empty] | Awareness NRL list of pointers not displaying correctly on NCRS | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | NRL Guidance issued to users of NCRS and included in the business change resources.
[5 empty] | Awareness Healthcare organisation unable/fails to update NRL pointer information | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | NRL Guidance issued to users of NCRS and included in the business change resources.
[5 empty] | Awareness Incorrect NHS number entered by NRL pointer provider (could impact 2 patients records) | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | NRL Guidance issued to users of NCRS and included in the business change resources.
[5 empty] | Awareness NRL patient record presentational issues (e.g. format, rendering etc.) | Integrating National Record Locator with the National Patient Information Service (NPIS) to allow for documents retrieval as part of Phase 2 NRL implementation | NCRS-331 | NRL Guidance issued to users of NCRS and included in the business change resources.
[6 empty] | NRL programme have a set of controls over NRL record published. | NRL Hazard 2, 4, 5, 6, 7, 8, 9 and 10
[5 empty] | Awareness Lack of adherence to clinical record standards | NRL programme have minimum control over record standards published via NRL: ref. NRL Hazard 1, 2, 4, 7, 9, 10 and 11
Development and adherence to clinical standards for NRL service are taken into account by the NCRS Development Team.
[5 empty] | Awareness Lack of clinical record standards | NRL programme have minimum control over record standards published via NRL: ref. NRL Hazard 1, 2, 4, 7, 9, 10 and 11
[5 empty] | Awareness Familiarity of users to existing SCRa may find it difficult to find relevant clinical information in NCRS | The NCRS should replicate what happens in the existing SCRa with the only difference being how the information is displayed when a Core SCR or SCR with Additional Information is available. | NCRS-67 | Training highlights where there is a difference between current SCRa and NCRS. |  | Addressing user feedback is an ongoing priority for the NCRS development team. Feedback received via various channels is prioritised for development with input from Live Services. | https://nhsd-confluence.digital.nhs.uk/display/CLP/Simplified+view+of+priorities
[6 empty] | The text used in the interface has been aligned to current messages to patients and professionals. There is ongoing user research to validate the text used and changes will be considered based on feedback. | https://hscic365.sharepoint.com/:x:/r/sites/NationalCareRecordsService/Shared%20Documents/General/User%20Research/Survey/Survey%20response%20log.xlsx?d=wd23a503c0bce4596ac94c68ddc3d2fa2&csf=1&web=1
[5 empty] | Misleading content in data source consumed by NCRS (e.g. CP-IS, Reasonable adjustments record). Including system error (information presented incorrectly) and human error (user not using the functionality as intended) | The RA Flag team have existing controls in places for ensuring correct display of the flag and its content: ref. RAF002, RAF006, RAF010 |  | User training material has been collated for a central web page to which a link has been provided within a bulletin in NCRS. | https://digital.nhs.uk/services/national-care-records-service/user-guidance RA specific: https://learninghub.nhs.uk/Resource/48879/Item
(CP-IS) All suppliers systems that integrates with CP-IS must adhere to the programme assurance requirements: ref. CP-IS Hazard 6.
(CP-IS) Local Authorities' staffs training by the CPIS programme in the use of their service: ref. CP-IS Hazard 9 and 10.
[5 empty] | Awareness Failure to display an indicator to warn user that additional Spine / Patient Flag Service resources exist (e.g. SCR, Reasonable Adjustments record, CP-IS, FGM-IS, COVID Vaccinations) | The display of flags/alerts/indicators in NCRS follows an established pattern which has been thoroughly tested with users. | RA: FLAGSAPI-135 FGM-IS: NCRS-869, FLAGSAPI-147 CP-IS: NRL: SCR:
[6 empty] | When selecting a role to access NCRS, the role name makes it clear that it is associated either with "clinical" or "admin" functionality. | https://digital.nhs.uk/binaries/content/assets/legacy/excel/5/b/rbac_database_27.2.xls
[6 empty] | Customised user journey whereby admin staff land directly on the "Patient detials" tab. Any user with at least one "clinical" RBAC activity code is considered a "clinical" user and will therefore land on the "Overview" tab. | NCRS-2874
[5 empty] | Awareness The information contained in the CP-IS Service is out of date; e.g. delay uploading revised CP-IS data from the Local Authorities in Spine. | CP-IS is monitored regularly by their Ops team: ref. CP-IS Hazard 5.
[5 empty] | Display of information via devices outside of recommended specification (size / aspect ratio / resolution) may make information open to misinterpretation or unusable. | Ensuring the application flows consistently and in a usable fashion on a mobile screen across both phone-sized and tablet-sized devices so that users on different devices have a consistent user experience and are confident that the data is displayed as expected. | NCRS-122 |  |  | Local conformance with Warranted Environment Specification (WES) | https://digital.nhs.uk/services/national-care-records-service#implementation
[6 empty] | Adopting a mobile responsive framework so that the product scales and displays correctly on a mobile device as well as on desktops - essentially, the product can scale to any screen size and orientation (buttons need to be easy to locate and click, there should be no horizontal scrolling required) | NCRS-1
[5 empty] | Awareness Poor Local Authority data issued to CP-IS. | All suppliers systems that integrates with CP-IS must adhere to the programme assurance requirements: ref. CP-IS Hazard 6.
Local Authorities' staffs training by the CPIS programme in the use of their service: ref. CP-IS Hazard 9 and 10.
[5 empty] | NCRS is launched (e.g. via "Deep Link") in a browser window in a way that obscures the information presented (e.g. too small or positioned behind another window) |  |  | User Guidance
[5 empty] | Awareness Data within a summary care record will be displayed regardless of the age (effective date) of the data item in question. |  |  | SCR Viewing Guidance | https://digital.nhs.uk/services/summary-care-records-scr/viewing-guidance-including-additional-information
[5 empty] | Defect in system, data source, or other connecting system | Ensure regular automated regression testing in to the overnight build in order to monitor that the NCRS product, once live, is not affected by browser updates. Daily healthchecks run by TechOps. | NCRS-802 | Training / guidance advising users that NCRS should not be used in isolation and that other sources of information should be consulted. |  | Organisations using NCRS are responsible for implementing local policies and processes to keep browsers up to date. This is communicated via the NCRS onboarding process.
[5 empty] | Awareness Incomplete display of a record consumed by NCRS (e.g. some or all items missing from a Reasonable Adjustments record) | Adding Reasonable Adjustments feature to NCRS | NCRS-969, NCRS-1631, FLAGSAPI-135
[6 empty] | Updating NCRS to display underlying conditions | NCRS-2423
[5 empty] | Awareness The display of underlying conditions is malformed e.g. rendering issues when multiple underlying conditions are present or long supporting comments are provided leading to text truncation issues | Reasonable Adjustments are always displayed above underlying conditions when viewing an RA record | NCRS-2423
[5 empty] | Awareness Error in implementation (by third-party systems) of APIs whereby "original term text" not maintained when communicating clinical codes (e.g. Snomed terms). | NCRS will surface the "display value" associated with a received Snomed Concept ID will be displayed in NCRS: the system will not query Snomed to find alternative display values.
[6 empty] | Reasonable Adjustments API specification requires connecting systems to maintain "original term text" when sending Snomed concepts to Spine | RAC003 and RAU004
[5 empty] | Awareness A Spine resource for a patient has either a large amount of individual entries or an entry with a large amount of associated information. |  |  | Generic training / guidance materials advised users of a "less is more" approach | https://digital.nhs.uk/services/reasonable-adjustment-flag
[5 empty] | Printing error: | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A
[5 empty] | With the exception of the SCR, no content displayed within NCRS has been optimised for printing. Therefore, printing NCRS content using the local browser's print functionality or by taking a screenshot may introduce clinical safety risks related to, among other things, layout, font, and truncation. For example: 1. Screenshot or Printed document is not an accurate representation of the patient's record (loss of context) 2. Screenshot or Printed document does not contain the date when the record was last time updated (""Summary created:..."") | With the exception of the SCR, NCRS has not been optimised for printing. |  | User Guidance - advice given is to not print (except the SCR)
4 | 2023-01-05 | The creation, update or removal of a Spine resource and/or its content is incorrect or unsuccessful | The creation, update, or removal of a Spine resource and/or its content is inappropriate/incorrect or is not uploaded to Spine. The user is not aware of missing information or is not notified of the failure to upload a change to Spine. | Inappropriate treatment or delay to care | Awareness Upload message to Spine/Reasonable Adjustments record is corrupt or incomplete | Adding National Reasonable Adjustments record to NCRS | NCRS-969, NCRS-1631 |  |  |  |  | Major | Low | 3 | [7 empty] | Considerable | Low | 2
[5 empty] | Awareness Error storing a resource (e.g. RA record, FGM-IS indicator) on Spine/Database | NHS England assurance and monitoring process in place to ensure reliable access and storage of the RA Flag on creation, update and removal of the flag
[5 empty] | Wrong RBAC permissions (user having the wrong permission or system using a non-standard RBAC) | Relevant RBAC activity codes (for features such as SCR, FGM-IS, and RA) are contained within the baseline for all Clinical Provision roles (with the exception of student and bank access roles). |  | Local processes in place (managed by Registration Authorities) to ensure that user permissions are correctly applied. | https://digital.nhs.uk/services/registration-authorities-and-smartcards#registration-authorities | Guidance and training provided relating specifically to the application of RBAC activity codes for the various features available in NCRS
[5 empty] | Loss of connectivity with Spine | NHS England assurance and monitoring process in place to ensure reliable access and storage of the RA Flag on creation, update and removal of the flag
[6 empty] | A message to notify the user of loss of internet connection appears automatically. | NCRS-358 | Training / guidance advising users that they will be unable to return to the patient’s demographics or SCR and perform another search until reconnected to the internet if they navigate back to the search page during loss of internet connection.
[6 empty] | User can continue to navigate around a patient’s record if internet connection is lost at the time of access (for up to 30 min) so that provision of care to patient is undisrupted. | NCRS-84 NCRS-340
[5 empty] | User creates a record / resource (e.g. RA record, FGM-IS) for a patient who is not eligible for that type of record / resource. | Users must confirm that a patient meets the eligibility criteria before creating a Reasonable Adjustment record. Relevant links to the Equality Act are provided within the NCRS application. |  | Generic training / guiance materials informs users about the eligiblity criteria and that RA records must only be created for eligible patients. Links to the Equality Act and the Equality Act definition of "disability" are provided. | https://digital.nhs.uk/services/reasonable-adjustment-flag/guide-to-using-the-reasonable-adjustment-flag-in-ncrs https://learninghub.nhs.uk/Resource/48879/Item
[6 empty] | NCRS UI prevents addition of records where the patient doesn't meet the relevant eligibility requirements (e.g. FGM-IS indicator cannot be added where patient is male or >18yo) | FLAGSAPI-147 and NCRS-869
[5 empty] | User does not use the "best interest" option when it is necessary to create/add, update or delete the Reasonable Adjustments record |  |  | User guidance relating to Reasonable Adjustments in NCRS | https://digital.nhs.uk/services/reasonable-adjustment-flag/guide-to-using-the-reasonable-adjustment-flag-in-ncrs
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | Local systems/processes may not be familiar with or have access to National Services made available via NCRS e.g. Reasonable Adjustments, FGM-IS, etc. |  |  | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance | NHS England raising awareness of Reasonable Adjustments via national comms.
Local existing processes remain in place for sharing reasonable adjustments (e.g. "care passport" printed)
[5 empty] | The User removes the content from the wrong patient via NCRS (currently relating to the following features: FGM-IS, Reasonable Adjustments and Personal Demographic Service). | The RA Flag team have existing controls in places for ensuring appropriate and successful deletion of an entire flag. | RAF003 | Training and guidance to be issued by NHS England informing HCP of the consequences of inappropriate removal of content and the fact that content should only be removed with the agreement of the patient or their legal proxy or in the best interest of the patient. | https://digital.nhs.uk/services/reasonable-adjustment-flag/guide-to-using-the-reasonable-adjustment-flag-in-ncrs | HCP should contact the original author of the content if unsure.
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | Confusion in a local record: content inappropriately removed from a Reasonable Adjustments record | The RA Flag team have existing controls in places for ensuring appropriate and successful deletion of an entire flag. | RAF003 | Training and guidance to be issued by NHS England informing HCP of the consequences of inappropriate removal of content and the fact that content should only be removed with the agreement of the patient or their legal proxy or in the best interest of the patient. |  | HCP should contact the original author of the content if unsure.
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | The User removes content due to having a different opinion. | Reasons associated with the removal must be stored on Spine Clinicals in order that this information is available for auditing purposes on request from NHS England [SPII-26166] | SPII-28864, SPII-26872 | Training and guidance to be issued by NHS England informing HCP of the consequences of inappropriate removal of content and the fact that content should only be removed with the agreement of the patient or their legal proxy or in the best interest of the patient. | https://digital.nhs.uk/services/reasonable-adjustment-flag/guide-to-using-the-reasonable-adjustment-flag-in-ncrs | HCP should contact the original author of the content if unsure.
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | User error when creating or updating a given resource (e.g. RA record, FGM-IS, etc) e.g. irrelevant or not optimal code(s) added to record | Reasonable Adjustments specification ensures that underlying conditions are added individually by a user as opposed to automatically added or added in bulk | RAC003, RAU004 | Generic training / guidance materials advise users to select codes carefully from the local record to ensure that they are appropriate. | https://digital.nhs.uk/services/reasonable-adjustment-flag | Records can only be viewed by authorised HCP. Records should be created in line with the standard for creating records that are shared.
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | Awareness User fails to create/update a resource (e.g. RA record, FGM-IS, etc.) when it would be useful and appropriate to do so |  |  | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance | NHS England raising awareness of Reasonable Adjustments via national comms.
[5 empty] | Awareness Connecting system error when creating or updating a given resource (e.g. RA record, FGM-IS, etc) via an API whereby "original term text" associated with a Snomed concept is not maintained | Assurance requirements specifying the necessity of maintaining "original term text" | RAC003, RAU004
[5 empty] | Data (e.g. RA record, FGM-IS, etc) is added to the wrong patient record (this will affect two patient records) |  |  | Training and guidance issued by NHS England informing HCP of the consequences of inappropriate removal of content and the fact that content should only be removed with the agreement of the patient or their legal proxy or in the best interest of the patient. | RA specific: https://learninghub.nhs.uk/Resource/48879/Item | HCP should contact the original author of the content if unsure.
[8 empty] | https://digital.nhs.uk/services/national-care-records-service#what-we-deliver The above webpage for NCRS covers the avaiable NCRS features and this includes FGM-IS. This webpage links to the service information for FGM-IS: https://digital.nhs.uk/services/female-genital-mutilation-information-sharing This url covers what the FGM-IS service is and includes useful resources and e-learning. This information includes how to record an FGM-IS indicator and also the processes that organisations are advised to follow to identify cases that then need to be recorded. "FGM Standards for Training Healthcare Professionals" describes the core competencies expected of "clinical and non-clinical staff with any contact with children and young people and/or parents/carers" and expands on the "Safeguarding children and young people: roles and competences for health care staff". The core competencies with regard to FGM training include: • Documents safeguarding/child protection concerns in order to be able to inform the relevant staff and agencies as necessary. • Maintains appropriate record keeping, and differentiates between fact and opinion. • Shares appropriate and relevant information with other teams/agencies. https://www.england.nhs.uk/wp-content/uploads/2018/04/fgm-standards-for-training-healthcare-professionals-1.pdf This mitigation is owned and managed by NHS England.J137 | https://digital.nhs.uk/services/female-genital-mutilation-information-sharing#useful-resources
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | Data (inc. either a whole record or an aspect of it (e.g. RA record, FGM-IS, etc)) is incorrectly removed from patient record |  |  | https://digital.nhs.uk/services/national-care-records-service#what-we-deliver The above webpage for NCRS covers the avaiable NCRS features and this includes FGM-IS. This webpage links to the service information for FGM-IS: https://digital.nhs.uk/services/female-genital-mutilation-information-sharing This url covers what the FGM-IS service is and includes useful resources and e-learning. This information includes how to record an FGM-IS indicator and also the processes that organisations are advised to follow to identify cases that then need to be recorded. "FGM Standards for Training Healthcare Professionals" describes the core competencies expected of "clinical and non-clinical staff with any contact with children and young people and/or parents/carers" and expands on the "Safeguarding children and young people: roles and competences for health care staff". The core competencies with regard to FGM training include: • Documents safeguarding/child protection concerns in order to be able to inform the relevant staff and agencies as necessary. • Maintains appropriate record keeping, and differentiates between fact and opinion. • Shares appropriate and relevant information with other teams/agencies. https://www.england.nhs.uk/wp-content/uploads/2018/04/fgm-standards-for-training-healthcare-professionals-1.pdf This mitigation is owned and managed by NHS England.J137 | https://digital.nhs.uk/services/female-genital-mutilation-information-sharing#useful-resources
[6 empty] | User interface to include appropriate wording / guidance, informing HCP of the consequences of inappropriate removal of content. Wording will also state content should only be removed with the agreement of the patient or their legal proxy or in the best interest of the patient. User is prompted to enter a reason and is given the opportunity to cancel. Additional wording stating that HCP should contact the original author of the content if unsure. | SPII-29076, SPII-28273 | Training and guidance to be issued by NHS England informing HCP of the consequences of inappropriate removal of content and the fact that content should only be removed with the agreement of the patient or their legal proxy or in the best interest of the patient. | RA specific: https://learninghub.nhs.uk/Resource/48879/Item https://digital.nhs.uk/services/reasonable-adjustment-flag/guide-to-using-the-reasonable-adjustment-flag-in-ncrs | HCP should contact the original author of the content if unsure.
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | Where two patients, A and B, both have FGM-IS indicators and/or Reasonable Adjustments flag information, user incorrectly removes the indicator (or part thereof) from the record of patient B rather than from the record of patient A (this will affect two patient records) |  |  | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[8 empty] | https://digital.nhs.uk/services/national-care-records-service#what-we-deliver The above webpage for NCRS covers the avaiable NCRS features and this includes FGM-IS. This webpage links to the service information for FGM-IS: https://digital.nhs.uk/services/female-genital-mutilation-information-sharing This url covers what the FGM-IS service is and includes useful resources and e-learning. This information includes how to record an FGM-IS indicator and also the processes that organisations are advised to follow to identify cases that then need to be recorded. "FGM Standards for Training Healthcare Professionals" describes the core competencies expected of "clinical and non-clinical staff with any contact with children and young people and/or parents/carers" and expands on the "Safeguarding children and young people: roles and competences for health care staff". The core competencies with regard to FGM training include: • Documents safeguarding/child protection concerns in order to be able to inform the relevant staff and agencies as necessary. • Maintains appropriate record keeping, and differentiates between fact and opinion. • Shares appropriate and relevant information with other teams/agencies. https://www.england.nhs.uk/wp-content/uploads/2018/04/fgm-standards-for-training-healthcare-professionals-1.pdf This mitigation is owned and managed by NHS England.J137 | https://digital.nhs.uk/services/female-genital-mutilation-information-sharing#useful-resources
[5 empty] | User deletes data without understanding the relevance of details/context deleted | Design requirements around the removal of data via NCRS. User is prompted to enter a reason and is given the opportunity to cancel. Warning messages inform the user about the consequences of removing data. | SPII-29076, SPII-28273 | Training and guidance issued by NHS England informing HCP of the consequences of inappropriate removal of content and the fact that content should only be removed with the agreement of the patient or their legal proxy or in the best interest of the patient. | RA specific: https://learninghub.nhs.uk/Resource/48879/Item | HCP should contact the original author of the content if unsure.
[8 empty] | https://digital.nhs.uk/services/national-care-records-service#what-we-deliver The above webpage for NCRS covers the avaiable NCRS features and this includes FGM-IS. This webpage links to the service information for FGM-IS: https://digital.nhs.uk/services/female-genital-mutilation-information-sharing This url covers what the FGM-IS service is and includes useful resources and e-learning. This information includes how to record an FGM-IS indicator and also the processes that organisations are advised to follow to identify cases that then need to be recorded. "FGM Standards for Training Healthcare Professionals" describes the core competencies expected of "clinical and non-clinical staff with any contact with children and young people and/or parents/carers" and expands on the "Safeguarding children and young people: roles and competences for health care staff". The core competencies with regard to FGM training include: • Documents safeguarding/child protection concerns in order to be able to inform the relevant staff and agencies as necessary. • Maintains appropriate record keeping, and differentiates between fact and opinion. • Shares appropriate and relevant information with other teams/agencies. https://www.england.nhs.uk/wp-content/uploads/2018/04/fgm-standards-for-training-healthcare-professionals-1.pdf This mitigation is owned and managed by NHS England.J137 | https://digital.nhs.uk/services/female-genital-mutilation-information-sharing#useful-resources
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | FGM family history exists for a patient but user doesn't record an FGM-IS indicator for that patient on Spine |  |  | https://digital.nhs.uk/services/national-care-records-service#what-we-deliver The above webpage for NCRS covers the avaiable NCRS features and this includes FGM-IS. This webpage links to the service information for FGM-IS: https://digital.nhs.uk/services/female-genital-mutilation-information-sharing This url covers what the FGM-IS service is and includes useful resources and e-learning. This information includes how to record an FGM-IS indicator and also the processes that organisations are advised to follow to identify cases that then need to be recorded. "FGM Standards for Training Healthcare Professionals" describes the core competencies expected of "clinical and non-clinical staff with any contact with children and young people and/or parents/carers" and expands on the "Safeguarding children and young people: roles and competences for health care staff". The core competencies with regard to FGM training include: • Documents safeguarding/child protection concerns in order to be able to inform the relevant staff and agencies as necessary. • Maintains appropriate record keeping, and differentiates between fact and opinion. • Shares appropriate and relevant information with other teams/agencies. https://www.england.nhs.uk/wp-content/uploads/2018/04/fgm-standards-for-training-healthcare-professionals-1.pdf This mitigation is owned and managed by NHS England.J137 | https://digital.nhs.uk/services/female-genital-mutilation-information-sharing#useful-resources
[8 empty] | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | Awareness Total or partial failure of messaging between NCRS and Spine/Database | Adding Reasonable Adjustments feature to NCRS | NCRS-969, NCRS-1631, FLAGSAPI-135 | https://digital.nhs.uk/services/national-care-records-service#what-we-deliver The above webpage for NCRS covers the avaiable NCRS features and this includes FGM-IS. This webpage links to the service information for FGM-IS: https://digital.nhs.uk/services/female-genital-mutilation-information-sharing This url covers what the FGM-IS service is and includes useful resources and e-learning. This information includes how to record an FGM-IS indicator and also the processes that organisations are advised to follow to identify cases that then need to be recorded. "FGM Standards for Training Healthcare Professionals" describes the core competencies expected of "clinical and non-clinical staff with any contact with children and young people and/or parents/carers" and expands on the "Safeguarding children and young people: roles and competences for health care staff". The core competencies with regard to FGM training include: • Documents safeguarding/child protection concerns in order to be able to inform the relevant staff and agencies as necessary. • Maintains appropriate record keeping, and differentiates between fact and opinion. • Shares appropriate and relevant information with other teams/agencies. https://www.england.nhs.uk/wp-content/uploads/2018/04/fgm-standards-for-training-healthcare-professionals-1.pdf This mitigation is owned and managed by NHS England.J137
[6 empty] | Adding FGM-IS feature to NCRS | NCRS-869, FLAGSAPI-147
[6 empty] | Handling failure scenarios when exact/potential duplicates are detected by Spine (BNA). | NCRS-1453 NCRS-1544
[6 empty] | Adding BNA feature to NCRS | NCRS-2514
https://digital.nhs.uk/services/female-genital-mutilation-information-sharing#useful-resources
[5 empty] | Awareness Error storing a resource (e.g. RA record, FGM-IS indicator) on Spine/Database | NHS England assurance and monitoring process in place to ensure reliable access and storage of the RA Flag on creation, update and removal of the flag
https://digital.nhs.uk/services/female-genital-mutilation-information-sharing#useful-resources
[5 empty] | Wrong RBAC permissions (user having the wrong permission or system using a non-standard RBAC) | Relevant RBAC activity codes (for both view and create FGM-IS indicator) are contained within the baseline for all Clinical Provision roles (with the exception of student and bank access roles). | https://digital.nhs.uk/binaries/content/assets/legacy/excel/5/b/rbac_database_27.2.xls
[8 empty] | https://digital.nhs.uk/services/national-care-records-service#what-we-deliver The above webpage for NCRS covers the avaiable NCRS features and this includes FGM-IS. This webpage links to the service information for FGM-IS: https://digital.nhs.uk/services/female-genital-mutilation-information-sharing This url covers what the FGM-IS service is and includes useful resources and e-learning. This information includes how to record an FGM-IS indicator and also the processes that organisations are advised to follow to identify cases that then need to be recorded. "FGM Standards for Training Healthcare Professionals" describes the core competencies expected of "clinical and non-clinical staff with any contact with children and young people and/or parents/carers" and expands on the "Safeguarding children and young people: roles and competences for health care staff". The core competencies with regard to FGM training include: • Documents safeguarding/child protection concerns in order to be able to inform the relevant staff and agencies as necessary. • Maintains appropriate record keeping, and differentiates between fact and opinion. • Shares appropriate and relevant information with other teams/agencies. https://www.england.nhs.uk/wp-content/uploads/2018/04/fgm-standards-for-training-healthcare-professionals-1.pdf This mitigation is owned and managed by NHS England.J137 | https://digital.nhs.uk/services/female-genital-mutilation-information-sharing#useful-resources
[5 empty] | Loss of connectivity to Spine/Database | A message to notify the user of loss of internet connection appears automatically. | NCRS-358 | Training / guidance advising users that they will be unable to return to the patient’s demographics or SCR and perform another search until reconnected to the internet if they navigate back to the search page during loss of internet connection.
[6 empty] | User can continue to navigate around a patient’s record if internet connection is lost at the time of access (for up to 30 min) so that provision of care to patient is undisrupted. | NCRS-84 NCRS-340
NHS England assurance and monitoring process in place to ensure reliable access and storage of the RA Flag on creation, update and removal of the flag
[5 empty] | CP-IS (ASN): | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A
[5 empty] | User error when selecting a role to log in with: User incorrectly selects role which includes B0107, views a CP-IS record, and generates an Access to Service Notification (ASN) when they shouldn't have | Description of the permissions associated with each available role profile (available on the "Select your role" page) updated to specify whether viewing a CP-IS record will generate an ASN. This helps the user to select the correct role. | NCRS-2585 | User training guide for the different roles, including retraining of existing CP-IS users. Particularly around RBAC activity codes. | To be provided by the CP-IS Programme | [6 empty] | Description of the permissions associated with each available role profile (available on the "Select your role" page) updated to specify whether viewing a CP-IS record will generate an ASN. This helps the user to select the correct role. | NCRS-2585 | User training guide for the different roles, including retraining of existing CP-IS users. Particularly around RBAC activity codes. | To be provided by the CP-IS Programme
[8 empty] | The NCRS and NHS England teams are in the process of updating some sections of relevant user guidance. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance | [6 empty] | Description of the permissions associated with each available role profile (available on the "Select your role" page) updated to specify whether viewing a CP-IS record will generate an ASN. This helps the user to select the correct role. | NCRS-2585
[5 empty] | User error when selecting a role to log in with: User incorrectly selects role which includes B0170, views a CP-IS record, and doesn't generate an Access to Service Notification (ASN) when they should have | Description of the permissions associated with each available role profile (available on the "Select your role" page) updated to specify whether viewing a CP-IS record will generate an ASN. This helps the user to select the correct role. | NCRS-2585 | User training guide for the different roles, including retraining of existing CP-IS users. Particularly around RBAC activity codes. | To be provided by the CP-IS Programme | [6 empty] | A warning message is dislpayed when viewing a CP-IS record in the scenario where no ASN is generated. Additional clarification also displayed above the "Previous Views" section informs users that this list is only updated when viewed in an emergency/unplanned care setting. | NCRS-2586
[6 empty] | A warning message is dislpayed when viewing a CP-IS record in the scenario where no ASN is generated. Additional clarification also displayed above the "Previous Views" section informs users that this list is only updated when viewed in an emergency/unplanned care setting. | NCRS-2586 | The NCRS and NHS England teams are in the process of updating some sections of relevant user guidance. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance | [6 empty] | Spine's default behavior is to generate an ASN except where an "isUnscheduledAccessEvent" value of "False" is present in the CPIS_Query | SPINECLI-14
[5 empty] | Awareness The CPIS_Query sent from NCRS to Spine does not contain the "isUnscheduledAccessEvent" flag meaning that an ASN is generated when it should not have been. | Spine's default behavior is to generate an ASN except where an "isUnscheduledAccessEvent" value of "False" is present in the CPIS_Query | SPINECLI-14 | [8 empty] | NCRS has been designed to populate the "isUnscheduledAccessEvent" flag correctly | NCRS-2559
[6 empty] | NCRS has been designed to populate the "isUnscheduledAccessEvent" flag correctly | NCRS-2559 | [8 empty] | Spine's default behavior is to generate an ASN except where an "isUnscheduledAccessEvent" value of "False" is present in the CPIS_Query | SPINECLI-14
[5 empty] | Awareness The "isUnscheduledAccessEvent" flag in the CPIS_Query sent from NCRS to Spine is populated incorrectly meaning that an ASN is incorrectly generated / not generated. | Spine's default behavior is to generate an ASN except where an "isUnscheduledAccessEvent" value of "False" is present in the CPIS_Query | SPINECLI-14 | [8 empty] | NCRS has been designed to populate the "isUnscheduledAccessEvent" flag correctly | NCRS-2559
[6 empty] | NCRS has been designed to populate the "isUnscheduledAccessEvent" flag correctly | NCRS-2559
[5 empty] | Birth Notifications | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | NA | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA
[5 empty] | User selects the wrong Child Health Units (CHU) when creating a Birth Notification either by mistake or because the list of available CHUs to select is out-of-date. |  |  | Key Operating Procedure exists for updating list of Child Health Units which ensures that the list of CHUs is maintained and up-to-date. | KOP-159
[8 empty] | Existing user guidance makes clear the importantance of selecting the correct CHU. | https://digital.nhs.uk/services/birth-notification-service/birth-notification-application-guide-for-maternity/registering-a-birth
[5 empty] | User creates and submits a Birth Notification from the wrong record i.e. attempts to find Mother's record but retrieves the wrong patient. |  |  | Existing user guidance makes clear the importantance of tracing the mother's record before creating a Birth Notification. | https://digital.nhs.uk/services/birth-notification-service/birth-notification-application-guide-for-maternity/registering-a-birth | Such issues can be resolved by the National Back Office (NBO)
[5 empty] | Incorrect data is pre-populated in a multiple birth scenario. | Creating another Birth Notification for the same mother | NCRS-1543
5 | 2023-01-05 | Flag / indicator / tab / content (inc. information) fatigue | User fails to identify the presence of a flag, indicator or tab including associated clinical information in a patient's record. | Inappropriate treatment or delay to care | Awareness A Spine resource for a patient has either a large amount of individual entries or an entry with a large amount of associated information. | NCRS has an established and consistently applied design pattern for displaying indicators/flags/alerts. This pattern has been validated with users and is followed by all relevant features within NCRS i.e. CP-IS, RA, and FGM-IS. | NCRS-1631 NCRS-1634 NCRS-869 |  |  |  |  | Considerable | Low | 2 | [7 empty] | Considerable | Low | 2
[5 empty] | The display of a tab/button/banner/indicator associated to a Spine resource is not apparent enough to a user. Note: See Additional Controls for further details for mitigations. | NCRS has an established and consistently applied design pattern for displaying indicators/flags/alerts. This pattern has been validated with users and is followed by all relevant features within NCRS i.e. CP-IS, RA, and FGM-IS. | NCRS-1631 NCRS-1634 NCRS-869 | [8 empty] | The Connecting System should ensure that their customers use browsers that are compliant with the Warrented Environment Specification. | https://digital.nhs.uk/services/spine/spine-technical-information-warrantied-environment-specification-wes
[5 empty] | User's behaviour/awareness leading to not considering the information presented as relevant or important. |  |  | Training/guidance provided to end users emphasising the need to consider every additional resources or information to a patient's record, where appropriate, in order to make the necessary adjustments to provide the best possible care. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance
[5 empty] | User who only has the CP-IS "Silent Read" RBAC Activity Code (B0170) may notice that a CP-IS flag exists for a patient but may choose not to view the record because they are concerned that not sending an ASN may be inappropriate. |  |  | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance | [8 empty] | User training guide for the different roles, including retraining of existing CP-IS users. Particularly around RBAC activity codes. | To be provided by the CP-IS Programme
6 | 2023-01-05 | Incorrect demographic details presented to user | User mistakenly believes they have retrieved the wrong patient record or acts on incorrect information (e.g. contact details). | Inappropriate treatment or delay to care | An erroneous change to a demographic record (e.g. contact details) could lead to subsequent confusion when that record is retrieved by another user. | Adding PDS edit feature to the new NCRS application | NCRS-1011 | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. This also includes advise on the safe use of the PDS Edit feature. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance |  |  | Considerable | Low | 2 | [7 empty] | Considerable | Low | 2
[6 empty] | Logging of all PDS Edit activities in NCRS for auditing and gathering feedback | NCRS-1015
[6 empty] | Controlling access to PDS Edit functionality on NCRS | NCRS-1013, NCRS-2004
[6 empty] | Displaying of warnings in the interface | NCRS-1078, NCRS-2107, KF2106
RBAC model clearly identifies what permissions are needed to gain access to the various features available via NCRS (e.g. editing a demographic record).
7 | 2023-01-05 | Confusion of two or more patient records | User fails to differentiate between multiple patient records and enters data in the wrong patient record or acts on data relating to a different patient. | Inappropriate treatment or delay to care | An erroneous change to a demographic record (e.g. contact details) could lead to subsequent confusion when that record is retrieved by another user. | Adding PDS edit feature to the new NCRS application | NCRS-1011 | NHS England provide NCRS Users with guidance related to the NCRS service and the features available within it. This also includes advise on the safe use of the PDS Edit feature. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance |  |  | Considerable | Low | 2 | [7 empty] | Considerable | Low | 2
[6 empty] | Logging of all PDS Edit activities in NCRS for auditing and gathering feedback | NCRS-1015
[6 empty] | Controlling access to PDS Edit functionality on NCRS | NCRS-1013, NCRS-2004
[6 empty] | Displaying of warnings in the interface | NCRS-1078, NCRS-2107, KF2106
RBAC model clearly identifies what permissions are needed to gain access to the various features available via NCRS (e.g. editing a demographic record).
[5 empty] | Broad search parameters (e.g. via Postcode search) return multiple patients among which two or more patients with similar details appear. | The onboarding process inlcudes a connection requirement for PDS accreditation. | NCRS-PDS-01 - Personal Demographic Service (PDS) Service | Training/guidance documentation has been updated to advise on effective use of the Postcode Search feature. NCRS-specific training guidance is shared with connecting organisations which now includes patient searching guidance. This guidance now includes information specifically about using the postcode search which reinforces the need to take particular care to identify the correct patient when using this function. | https://digital.nhs.uk/services/national-care-records-service https://digital.nhs.uk/services/national-care-records-service/user-guidance | The postcode search feature (NCRS-502) is only available to users with activity code B0098. The national RBAC database states that: "This activity must only be allocated to a limited number (3 to 4) of correctly trained demographics staff working in a local back office environment either at a Trust or national level."
Note on C4: What has happened in the technical context (e.g. in NCRS) that shouldn't happen
Note on D4: Potential for harm - people context
Note on E4: Patient context. What might happen to the patient.

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## References
Reference | Description | Version | Doc. No.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16