## NHS login Integration Plan
| NHS login | [6 empty] | #VALUE!
Done | Integration Plan
Not Done | This is an optional part of the NHS login Integration Toolkit. It is intended to be a helpful checklist and guide to the main activities required to integrate your product with NHS login.
Not Applicable | See the main NHS login Integration Toolkit website for more information.
Please email engage.nhslogin@nhs.net, or contact your assigned NHS login Integration Project Manager, if you have any questions about when to use the form or how to complete it. Please complete all green fields.
#REF! | Partner Name: | [5 empty] | Product Name:
| Step |  |  | Description |  | Form / Useful Links (As Applicable) | Further Information | Completed | Date Completed or Submitted
1 of 4: Apply for NHS login
| 1 | Check eligibility for NHS login |  | NHS login allows patient access to patient facing services Your service must: - be patient facing - offer a health or social care benefit - be commissioned (contracted) or sponsored in development by an NHS or Social Care organisation - be free at the point of delivery - be compliant with DAPB3051 for ID Verification and Authentication |  | None | See our eligibility criteria at: https://digital.nhs.uk/services/nhs-login/nhs-login-for-partners-and-developers/nhs-login-integration-toolkit/apply-for-nhs-login |  | DD/MM/YYYY
| 2 | Review if NHS login fits your needs |  | Before you apply for NHS login, you should understand how NHS login works and make sure it fits your needs |  | None | NHS login for Partners and Developers |  | DD/MM/YYYY
How NHS login Works
| 3 | Ask any questions |  | Contact us if you have any questions |  | None | engage.nhslogin@nhs.net |  | DD/MM/YYYY
| 4 | Apply for NHS login |  | To apply for NHS login, please complete and send an NHS login Application from the NHS England Digital Onboarding Service |  | Find out how digital onboarding works and how to get started. You can access the digital onboarding portal at https://onboarding.prod.api.platform.nhs.uk/. | We will acknowledge receipt and ask questions. |  | DD/MM/YYYY
| 5 | Attend Application Review Call |  | This is a review call with the NHS login Integration Team. Combined with your completed NHS login application, we will agree next steps that can include a decision not to proceed or a decision to make an application to the Partner Integration Board |  | https://digital.nhs.uk/data-and-information/information-standards/governance/latest-activity/standards-and-collections/dcb3051-identity-verification-and-authentication-standard-for-digital-health-and-care-services | Agenda: - Your NHS login Application Form - Your assessment of your product to DAPB3051 NHS login team roles attending: - Programme Lead - Technical Architecture - Data Security - Information Governance |  | DD/MM/YYYY
NHS login Partner Integration Board (PIB) Decision: The Board will decide to either 'Approve' or 'Defer pending further information' or 'Reject' your application.
2 of 4: Discovery
| 6 | a | Decide what level of verification you need | Based on your assessment to DAPB3051, decide what level of identity verification and authentication is suitable for your product or service. |  | None | https://digital.nhs.uk/data-and-information/information-standards/information-standards-and-data-collections-including-extractions/publications-and-notifications/standards-and-collections/dcb3051-identity-verification-and-authentication-standard-for-digital-health-and-care-services |  | DD/MM/YYYY
|  | b | Define the Vector of Trust your product requires | Based on your level of ID Verification and Authentication, define the mapping to NHS login |  | None | https://nhsconnect.github.io/nhslogin/vectors-of-trust/ |  | DD/MM/YYYY
|  | c | Download the NHS login User Journey Visuals presentation | Describing the NHS login user journeys that start with the NHS login button on the home page of your app. These cannot be changed or customised. |  | None | https://digital.nhs.uk/services/nhs-login/nhs-login-for-partners-and-developers/nhs-login-integration-toolkit/discovery |  | DD/MM/YYYY
| 7 | Develop a Proof of Concept in the Sandpit and prepare user journey videos for the next stage calls |  | To understand how NHS login fits with your service, you need to build a proof of concept and explore the end-to-end journey in our Sandpit environment. The Sandpit is a copy of our production code environment. You cannot create a P9 account in the sandpit as there is no link to an ID Verification tool. Use our test data we send you. Sandpit is free to use! |  | Sandpit Test Environment Request Form | Step-by-step information on setting up the connection and guidance on testing scenarios is at: https://nhsconnect.github.io/nhslogin/ Read about the user journeys required for assurance at https://digital.nhs.uk/services/nhs-login/nhs-login-for-partners-and-developers/nhs-login-integration-toolkit/nhs-login-forms-and-documents |  | DD/MM/YYYY
| 8 | Review our NHS login 'Forms and documents' library |  | Review our document library to understand compliance, assurance and legal requirements. |  | None | https://digital.nhs.uk/services/nhs-login/nhs-login-for-partners-and-developers/nhs-login-integration-toolkit/nhs-login-forms-and-documents |  | DD/MM/YYYY
| 9 | Ask our developers any questions |  | You can use our Slack public developer channel to get answers to technical questions and see what other people are asking. Slack is free to sign up and use. |  | Sign up at: https://nhsconnect.github.io/nhslogin/developer-support/ | None |  | DD/MM/YYYY
| 10 | Review your resources, required expertise, and the development work needed |  | You need to review and decide if you have the resources to complete the work needed to integrate and go live. |  | None | None |  | DD/MM/YYYY
| 11 | Decide if you want to proceed and integrate with NHS login |  | Let us know if you want to proceed, or delay your application, or if you decide that NHS login is not right for you at this time so that we can either pause or close your application. |  | engage.nhslogin@nhs.net | None |  | DD/MM/YYYY
| 12 | a | Complete the Product Demonstration Call Request | Complete the 'Prepare for your Product Demonstration Call with NHS login' section of the DOS. Submit the completed section. |  | NHS England Digital Onboarding Service | None |  | DD/MM/YYYY
|  | b | Provide Additional Information (if requested) | After submitting, if there is anything we are unsure of, we will contact you to request clarification or additional information before the call. |  | None | None |  | DD/MM/YYYY
3 of 4: Integrate
| 13 | Attend Preparation Call |  | This is the first formal call with your designated Project Manager in the Integration Team. They are assigned to help you integrate with NHS login. |  | None | Agenda: - The NHS login Integration Process​ - Documentation​ - Project Plan to go-live​ - Preparation for the next call - Viewing your user-journeys as a live demo or video - Communications / Microsoft Teams​ |  | DD/MM/YYYY
Microsoft Teams Folder and Communication Channel Created A private and confidential shared folder and channel in Microsoft Teams will be created for you. This is for the purpose of sharing documentation and communicating with the NHS login Integration Team throughout the process of integrating with NHS login.
| 14 | a | Attend Product Demonstration Call | Defines the technical next steps and determines your go live date. Critical opportunity for you to demonstrate your prototype as a video or live demonstration from your work in the NHS login sandpit. The outcome willbe a go/no go to the next stage. Our subject matter experts can answer your questions, ask you questions and talk about available support. |  | None | Agenda: - Product Demonstration Technical architecture - User Journey videos or live demo - IG and data flows - Contracting NHS login team roles attending: - Technical Architecture - Data Security - Information Governance - Commercial - Project Manager |  | DD/MM/YYYY
| 15 | b | Provide Additional Information and/or Complete Actions (as requested) | After the Product Demonstration Call, missing or additional information may be requested, and actions completed. |  | None | None |  | DD/MM/YYYY
| 16 | Complete and submit the Integration Environment Request Form |  | a | Submit the Integration Test Environment Request Form for access to the NHS login Integration test environment | https://forms.office.com/pages/responsepage.aspx?id=slTDN7CF9UeyIge0jXdO46Wses3MagtDu1VtOYTOy5lURENWQVNNQk44OElMSUhEUzFCT1pNUVJFRS4u | We will send you a test data pack and your access credentials. See more information abou testing at https://nhsconnect.github.io/nhslogin/testing-scenarios/ |  | DD/MM/YYYY
|  |  |  | b | Request Custom Test Data (if required) |  |  |  | DD/MM/YYYY
|  |  |  | c | Complete your testing and assurance activities |  |  |  | DD/MM/YYYY
|  |  |  | d | Request your Test Conformance Certificate from NHS login. When received, please embed this in your SCAL | https://forms.office.com/pages/responsepage.aspx?id=slTDN7CF9UeyIge0jXdO47fiE9b713ZAoGlaQlJvbVpUQU1QV1QwUkpBWllaRENOWjVRQzlVSU5aUSQlQCN0PWcu | None |  | DD/MM/YYYY
Actions now taken by NHS England: Client configured with appropriate scopes & test pack issued to partner Custom Test Data returned via email (if applicable) Conformance Test Certificate issued to partner
| 17 | Complete the Supplier Conformance Assessment List (SCAL) |  | a | Complete the SCAL form that has been sent to you (including Test Evidence) to confirm that you have completed the integration requirements for NHS login. | Forms and documents | Please do not complete or modify the example forms. The NHS login Integration Team will provide you with your version in your MS Teams channel. |  | DD/MM/YYYY
| 18 | Complete the Connection Agreement |  | b | Complete the Connection Agreement that has been sent to you, or your connecting party, via email from NHS England Live Services. The agreement contains the key legal obligations NHS England and a connecting party must meet. | Forms and documents | Please do not complete or modify the example forms. NHS Digital Live Services team will email your Connection Agreement to review, sign and return to them |  | DD/MM/YYYY
Actions now taken by NHS England: Connection Agreement & SCAL reviewed and to be approved
| 19 | Complete and submit the Service Discovery Form |  | NHS login is supported by the NHS England National Service Desk. You must complete and submit a Service Discovery Form to use this service for NHS login, even if you are already registered. |  | Service Discovery Form | None |  | DD/MM/YYYY
Actions now taken by NHS England: National Service Desk account created (if required) Support desk configured (first line, second line and third line support) and confirmation issued to partner
| 20 | Contact all connected GP suppliers [IM1-integrated products only] |  | Contact all your connected GP suppliers and notify them of your plans to go live with NHS login. |  | None |  |  | DD/MM/YYYY
Actions now taken by NHS England: IM1 PFS API connection confirmed
| 21 | Raise a Request for Change (RFC) [IM1-integrated products only] |  | Raise an RFC with the IM1 team as usual. If you are not an IM1-integrated product, please indicate "Not Applicable". |  | im1.team@nhs.net | None |  | DD/MM/YYYY
23
| 22 | Request access to the Production (Live) Environment |  | Complete your Production Environment Request Form. Note: Board approval is required before you go live so we won't enable the form until after it is given, but you can submit the form ahead of the PIB meeting. |  | https://forms.office.com/pages/responsepage.aspx?id=slTDN7CF9UeyIge0jXdO46Wses3MagtDu1VtOYTOy5lURENWQVNNQk44OElMSUhEUzFCT1pNUVJFRS4u | None |  | DD/MM/YYYY
Actions now taken by NHS England: Project Manager presents an application to the NHS login PIB and asks members to approve your go live (or not) Project Manager confirms the outcome with you and agrees your go live date.
4 of 4: Go live and support
| 23 | Go Live date |  | NHS login support will send you go live confirmation on your agreed 'go live' date. Your named project manager will email and/or MS Teams message you the live support details. |  | None | https://digital.nhs.uk/services/nhs-login/nhs-login-for-partners-and-developers/nhs-login-integration-toolkit/go-live-and-support |  | Not Applicable
Actions now taken by NHS England: Handover to Live Account Support Team
| 24 | a | Service and Incident Management | If you have a problem or incident with NHS login, you should visit the Partner service management page. |  | None | https://digital.nhs.uk/services/nhs-login/nhs-login-for-partners-and-developers/nhs-login-integration-toolkit/partner-service-management | Not Applicable | Not Applicable
|  | b | Help for NHS login users | Find helpful information, guidance, and support for users of NHS login at our Help Centre. |  | None | NHS login Help Centre
|  | c | NHS login change and release process | Follow our latest service updates, see a roadmap of upcoming features and learn more about known service issues on our Service updates and releases page. |  | None | https://digital.nhs.uk/services/nhs-login/nhs-login-for-partners-and-developers/service-updates-and-releases
|  | e | Live partner change requests | Complete the Live Partner Change Request Form if you need to make changes to your NHS login configuration, or request additional features, after you go live. |  | NHS login Change Request Form | None
|  | f | Communications guidance | We provide all integrated services with guidance and assets that communications professionals can refer to when planning marketing activity around their products. |  | Hosted in your MS Teams channel | None